| Name of Individual / Organisation | All Star Entertainment |
| --- | --- |
| Name of Project | M62 Creative Corridor Youth Empowerment Programme (Block Party) |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

| START DATE | END DATE | ACTIVITY / TASK |
| --- | --- | --- |
| 18/08/16 | 28/10/16 | Research and Development of project. Putting Project plans in place. Speaking with partners. Putting recruitment plans in place. Securing venues and workshop spaces. Recruiting artists/ trainees etc. Putting marketing and communication plans in place. Putting evaluation plans in place |
| 30/01/17 | 30/01/17 | Press Release out |
| 16/02/17 | 16/02/17 | Launch Event |
| 19/04/17 | 20/04/17 | BLOCK PARTY! 1 Tasters/workshops and sharing event The HIVE Youth Hub Birkenhead,Merseyside |
| 27/04/17 | 28/04/17 | BLOCK PARTY! 2 Tasters/ workshops and sharing event - Make Liverpool |
| 29/04/17 | 30/04/17 | BLOCK PARTY! 3 Tasters/ workshops and sharing event - Salford |
| 24/05/17 | 25/05/17 | BLOCK PARTY! 4 Tasters/ workshops and sharing event - Bradford |
| 25/08/17 | 27/08/17 | BLOCK PARTY! 5 Tasters/ workshops and main event - Australia Houses HULL 2017 |
| 14/10/17 | 14/10/17 | Evaluation and sharing from programme gathered by this date |
| 14/10/17 | 14/10/17 | Launch of Hull Block Party Creatives Collective |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances