PRSF NEW MUSIC BIENNIAL

HULL

29th JUNE to 2nd JULY 2017

ARTIST PACK

ARTIST: Anna Meredith

ARTIST CONTACT (Mobile number): TBC – PROMOTER TO CONFIRM

Management – ?

VENUE: Albermarle Music Centre

Address: Albermarle Music Centre, 60 Ferensway, Hull HU2 8LN

Phone: 01482 318800

LOADING IN FROM:

PARKING REQUIREMENT and LOCATION:

TBC – PROMOTER TO CONFIRM

PERSONNEL

STAGE MANAGER (Primary contact show weekend only): ??

PRODUCTION MANAGER: Gareth Hughes – 07733112272

PRODUCTION ASSISTANT: Joanna Morley – 07725 942808

VENUE CONTACT: ??

DATE AND TIME OF PERFORMANCE: Friday 30th June 17:30 (45mins)

PRODUCTION SCHEDULE:

THURSDAY 29 JUNE. 09:00 - 18:00 (ACCESS); 09:00; Stage manager on site. DAY; Delivery of Harmonium (Gavin Bryars). DAY; Set up dressing rooms. DAY; Dressing and branding. DAY; BBC to park up to the corner / rear. 12noon; Tech set up. 12noon; Set up Anna Meredith - percussion set up (see also Hannah Peel plot). FRIDAY 30 JUNE. 09:00 - 23:00 (ACCESS); 09:00; Stage manager on site - set for Anna Meredith. 09:00; BBC OB in. 10:00; Anna Meredith - Artists arrive. 11:00 - 12:00; Anna Meredith - Set up. 13:00 - 16:00; Anna Meredith - rehearsal. 16:30; Box office on site. 17:00; Doors. 17:30; Anna Meredith PERFORMANCE. 18:15; FINISH. 18:30 - 18:45; Reset for Gavin Bryars. 18:45; Rehearsal Gavin Bryars. 19:00 - 21:00; Moulettes rehearsal - rehearsal - Rivers and Railways. 19:45; Doors. 20:00; Gavin Bryars - PERFORMANCE. 20:45; FINISH. 21:00 - 23:00; Reset for Hannah Peel and Laurence Crane. 21:00 - 23:00; Reset Dressing rooms. SATURDAY 1 JULY. 09:00 - 21:00 (ACCESS); 09:00; Stage manager on site. 10:00; Artists arrive - Laurence Crane. 11:00 - 12:15; Laurence Crane - rehearsal. 12:00; Box office on site. 12:15; Doors. 12:30; Laurence Crane - PERFORMANCE. 13:15; FINISH. 13:30; Hannah Peel - Artists arrive - rehearsal synthesisers and percussion. 15:30; Hannah Peel - Brass arrives - rehearsal. 16:15; Doors. 16:30; Hannah Peel - PERFORMANCE. 17:15; FINISH. 17:30; Set tech for Jocelyn Pook. 21:00; Clear. SUNDAY 2 JULY. 09:00 - 21:00 (ACCESS); 09:00; Stage Manager on site. 10:00; Artists arrive - Jocelyn Pook. 10:00 - 14:00; Jocelyn rehearsals. 14:00; Box office on site. 14:45; Doors. 15:00; Jocelyn Pook - PERFORMANCE. 15:45; FINISH. 16:00 - 20:00; Clear and derig.

TECHNICAL

Sound

FOH Control

1 Midas Pro 2C - Live Audio System

Speaker System

6 L Acoustics - ARCS

8 L Acoustic ARCS - ARCOUPL

2 Ratchet Strap (Black) - 7.5m 2T

4 L Acoustics - SB28

1 L Acoustics LA8 Rack (4 - Way)

2 NL4 Speakon Cable 4mm 20m

2 NL4 Speakon Cable 4mm 10m

2 NL4 Speakon Cable 4mm 5m

4 NL4 Speakon Cable 4mm 0.5m

3 NL4 Sub Split Cable

Monitor System (Up to 4x Mixes)

4 L Acoustic 115XT HiQ

Microphones

1 Shure ULXP Beta58 Handheld Radio System - CH38

Misc

1 63A 3-Phase Cable 20m

1 63A 3 Phase Mains Distro #5

1 Backline Power Prep - Standard

Staff

1 Engineer - FOH

1 Engineer – Systems

AV

Material

1 Blackmagic Design HDMI-SDI Converter

1 Blackmagic Design SDI-HDMI Converter

1 Black Magic ATEM 1 M/E Production Studio 4K

Staff

1 Engineer - AV

Lighting

Provided by House

Staff

1 Engineer – Lighting

Headphone Monitoring – Tubular Brass

Material

1 Art Head Amp 6

1 Closed Back Headphones

1 10m Balanced Jack Cable

1 5m Balanced Jack Cable

1 Jack to Jack Coupler

1 3.5mm to 6.35mm Jack Adapter

2 BSS AR133 DI

Microphones – Jocelyn Pook

RF

1 DPA 4088F - Headset Microphone

1 DPA DAD6034 - Microdot to 3.5mm Jack

1 Sennheiser EW512 G3 - Belt Pack System - Range GB

Microphones

3 Neumann KMS-105

3 AKG C451

3 AKG C414ULS

10 Microphone Stand – Tall

Microphones – Tubluar Brass

Material

6 BSS AR133 DI

2 AKG C451

1 Shure Beta 57

3 Microphone Stand – Tall

Microphone – Gavin Bryars

Material

1 Sennheiser e609

2 DPA DAD 4099-BC

1 DPA Clip for Violin and Mandolin (VC4099)

1 DPA Clip for Cello (CC4099)

2 DPA DAD 6001 XLR 48 volt adapter

1 Shure Beta 87

2 Shure SM57

2 BSS AR133 DI

1 Microphone Stand - Tall

2 Microphone Stand - Medium

1 Microphone Stand - Short

RIDER:

TBC

BACKLINE:

| BACKLINE | 3 Full drumkits; | ALBEMARLE |
| --- | --- | --- |
|  | Kit BD + pedal | ALBEMARLE |
|  | Floor Tom | ALBEMARLE |
|  | Snare Drum + stand | ALBEMARLE |
|  | 2 kit toms (high / medium) | ALBEMARLE |
|  | Hi-Hat | ALBEMARLE |
|  | Crash Cymbal | ALBEMARLE |
|  | Drum stool | ALBEMARLE |
|  | Drum mat (depending on the flooring! On wooden floors things can easily slip and this is very involved with pedals etc.) | ALBEMARLE |

ACCREDITATION

David & Alice Porter (Directors)

Steve & Sam Shaw (Directors)

Peter & Lorraine Boardman (Directors)

Wes Zepherin (Director)

Kirsty & Gary Halliday (Marketing)

Ben Pugh (Production)

??Artists are Nick Blacka, Rob Turner, Chris Illingworth,

Sound Joe Reiser

Manager Kerstan Mackness