## Sheet1
Production | The Last Ballad of Lillian Bilocca
Venue | Guildhall, Hull
Artform | Site Specific
Reh weeks (inc Tech) | 5 | Actors | 8 | Subsistence | 200
Running Weeks | 2 | Musicians | 6 | No of Perfs | 14 | Capacity | 200
SUMMARY | DEPARTMENT | [9 empty] | BUDGET | FORECAST | DIFFERENCE | NOTES
| ZK101 - COMMISSIONING & FEES | [9 empty] | 2772 | 38772 | -36000 | Royalties
| ZK102 - DEVELOPMENT & R&D | [9 empty] | 5250 | 5250 | 0 | Commission for script & music included here
| ZK103 - CREATIVE TEAM, PRODUCTION TEAM & CONSULTANTS | [9 empty] | 131626.1067 | 119525.6667 | 12100.44
| ZK104 - PERFORMERS AND MUSICIANS | [9 empty] | 72954.1867 | 47754.1867 | 25200
| ZK105 - REHEARSAL COSTS | [9 empty] | 4750 | 4750 | 0
| ZK106 - TECHNICAL & PRODUCTION | [9 empty] | 67800 | 67400 | 400
| ZK107 - VENUE & LOGISTICS | [9 empty] | 19625 | 19625 | 0
| ZK108 - PROGRAMME LEGAL & DOCUMENTATION | [9 empty] | 3500 | 3500 | 0
| ZK109 - PROGRAMME MARKETING, DIGITAL & COMMS | [9 empty] | 18000 | 18000 | 0
| ZK110 - PROGRAMME EDUCATION & COMMUNITY ENGAGEMENT | [9 empty] | 6500 | 6500 | 0
| ZK111 - PROGRAMME VOLUNTEERING | [9 empty] | 1050 | 1050 | 0
| ZK112 - ARTIST & GUEST LIAISON | [9 empty] | 1500 | 1500 | 0
| ZK113 - RUNNING COSTS | [9 empty] | 0 | 0 | 0
| ZK114 - ADMIN & MISC | [9 empty] | 500 | 500 | 0
| TOTAL | [9 empty] | 335827.2933 | 334126.8533 | 1700.44
[10 empty] | CHECK | 335827.2933 | 334126.8533 | 1700.44
| Net Box Office | 2200 | av net per perf | [7 empty] | 30800 | 30800 | 0 | Based on capacity of 200; AV £22 tickets (face value); 60% capacity of 200 = 120 paid tickets per night
| Hull 2017 Budget | [9 empty] | 300000 | 300000 | 0
| Balance | [9 empty] | -5027.2933 | -3326.8533 | -1700.44
ZK101 - COMMISSIONING & FEES | [10 empty] | BUDGET | FORECAST | DIFFERENCE | NOTES
| Visual art commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Music commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Drama commissioning & fees | 9% | Royalty of Net Box Office | [7 empty] | 2772 | 2772 | 0 | 6% author; 3% music & lyrics; available to cover licensing of extant music (Tariff T)
| SUB TOTAL | [9 empty] | 2772 | 2772 | 0
| Dance commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Comedy commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Circus commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Digital commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Literature commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Opera commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Major Project commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Film commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Photography commissioning & fees | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Technical & Production fees | [9 empty] | 0 | 36000 | -36000 | LA ADDED AM BUYOUT - CONTRACTED - FIRST INSTALEMENT PAID
| SUB TOTAL | [9 empty] | 0 | 36000 | -36000
| Grants | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| TOTAL COMMISSIONING & FEES | [9 empty] | 2772 | 38772 | -36000
ZK102 - DEVELOPMENT & R&D | [10 empty] | BUDGET | FORECAST | DIFFERENCE | NOTES
| R&D Fees | [9 empty] | 2250 | 2250 | 0 | Oct '16 R&D
| SUB TOTAL | [9 empty] | 2250 | 2250 | 0
| R&D Travel | [9 empty] | 500 | 500 | 0 | Oct '16 R&D
| SUB TOTAL | [9 empty] | 500 | 500 | 0
| R&D Hotels & accommodation | [9 empty] | 500 | 500 | 0 | Oct '16 R&D
| SUB TOTAL | [9 empty] | 500 | 500 | 0
| R&D Professional Fees | [9 empty] | 1500 | 1500 | 0
| SUB TOTAL | [9 empty] | 1500 | 1500 | 0
| R&D meeting & workshop costs | [9 empty] | 500 | 500 | 0
| SUB TOTAL | [9 empty] | 500 | 500 | 0
| Subsistence | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| TOTAL DEVELOPMENT & R&D | [9 empty] | 5250 | 5250 | 0
ZK103 - CREATIVE TEAM, PRODUCTION TEAM & CONSULTANTS | [10 empty] | BUDGET | FORECAST | DIFFERENCE | NOTES
Sub code | Details
| Consultant Costs | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
|  |  |  | BUDGET | FORECAST | BUDGET | FORECAST | BUDGET | FORECAST
| Lead Creatives | Names |  | Fee |  | Travel |  | Expenses
| Production Manager | TBC |  | 8000 | 9500 | 500 | 500 | 1000 | 1000 |  | 9500 | 11000 | -1500
| Casting Director | PJ |  | 3000 | 3000 | 300 | 300 | 0 | 0 |  | 3300 | 3300 | 0
| Writer | MP |  | 10000.44 | 10000 | 800 | 800 | 1200 | 1200 |  | 12000.44 | 12000 | 0.44 | £8000 fee; £55.54 per day for 6 days per week for 6 weeks;
| Composer | AM |  | 8500 | 0 | 800 | 0 | 1200 | 0 |  | 10500 | 0 | 10500 | LA REMOVED DUE TO BUYOUT ABOVE
| Director | SF |  | 8500 | 8500 | 800 | 800 | 1000 | 1000 |  | 10300 | 10300 | 0
| Asso Movement Director Community | JB |  | 4000 | 3000 | 500 | 500 | 500 | 1000 |  | 5000 | 4500 | 500
| Set & Costume Designer | AS |  | 8000 | 8000 | 800 | 800 | 1000 | 1000 |  | 9800 | 9800 | 0
| Fight Director | TBC |  | 700 | 700 | 300 | 300 | 0 | 0 |  | 1000 | 1000 | 0 | REQUIRED
| Lighting Designer | CD |  | 3000 | 3000 | 500 | 500 | 600 | 600 |  | 4100 | 4100 | 0
| Sound Designer | PM |  | 3000 | 3000 | 500 | 500 | 600 | 600 |  | 4100 | 4100 | 0
| Costume Supervisor |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Co-direction / Choreography | IK |  | 6400 | 7000 | 1000 | 600 | 1200 | 1000 |  | 8600 | 8600 | 0 | LA Increased. Needs accommodation Manc, Hull. Flag re travel/accomm for comms cast
| Prehearsal Pianist |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Voice |  |  | 1000 | 1000 | 0 | 0 | 250 | 250 |  | 1250 | 1250 | 0 | REQUIRED
| Musical Director / Supervisor |  |  | 1500 | 0 | 500 | 0 | 600 | 0 |  | 2600 | 0 | 2600 | LA REMOVED DUE TO BUYOUT ABOVE
| Consultants |  |  | 1600 | 1600 | 300 | 300 | 0 | 0 |  | 1900 | 1900 | 0
| Dramaturg |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
63200 | TOTALS |  |  | 67200.44 | 58300 | 7600 | 5900 | 9150 | 7650 |  | 83950.44 | 71850 | 12100.44
0
| Lead Creatives | [9 empty] | 67200.44 | 58300 | 8900.44
| SUB TOTAL | [9 empty] | 67200.44 | 58300 | 8900.44
0
| Assistant Creatives | [9 empty] | 0 | 0 | 0 | LA MOVED JB TO CREATIVES
| SUB TOTAL | [9 empty] | 0 | 0 | 0
0
| Creative Team Expenses | [9 empty] | 16750 | 13550 | 3200
| SUB TOTAL | [9 empty] | 16750 | 13550 | 3200
Sub code | Details | Rehearsals |  |  |  |  | Running |  |  |  | Total Run
| Production Team | Number of Production | Number Weeks | Weekly Salary | Total Salary | Subs & Travel | Weeks | Weekly Salary | Total salary | Subs & Travel | BUDGET | FORECAST | DIFFERENCE | NOTES
| Company Stage Manager | 1 | 5 | 600 | 3000 | 1000 | 2 | 600 | 1200 | 400 | 5600 | 5600 | 0
| Deputy Stage Manager | 1 | 5 | 500 | 2500 | 1000 | 2 | 500 | 1000 | 400 | 4900 | 4900 | 0
| Assistant Stage Manager | 1 | 5 | 450 | 2250 | 1000 | 2 | 450 | 900 | 400 | 4550 | 4550 | 0
| Assistant Stage Manager Comm Cast / Crew | 1 | 5 | 450 | 2250 | 1000 | 2 | 450 | 900 | 400 | 4550 | 4550 | 0
| Stage Management Overtime |  | 8% |  | 800 |  |  | 5% | 200 |  | 1000 | 1000 | 0 | LA ADDED 2nd ASM
| Stage Management NI |  | 13.8% |  |  |  |  | 13.8% | [5 empty] | NI not applicable
| Stage Management Holiday |  | 8.333% |  | 833.3333 |  |  | 8.333% | 333.3333 |  | 1166.6667 | 1166.6667 | 0 | LA ADDED 2nd ASM
| Stage Management Pensions |  | 3% |  | 300 |  |  | 3% | 120 |  | 420 | 420 | 0 | LA ADDED 2nd ASM
| Sound Production | 1 | 3 | 1000 | 3000 | 600 | 0 | 1000 | 0 | 0 | 3600 | 3600 | 0
| Sound No 1 | 1 | 2 | 600 | 1200 | 400 | 2 | 600 | 1200 | 400 | 3200 | 3200 | 0
| LX Production | 1 | 3 | 1000 | 3000 | 600 | 0 | 1000 | 0 | 0 | 3600 | 3600 | 0
| LX & Operator | 1 | 2 | 500 | 1000 | 400 | 2 | 500 | 1000 | 400 | 2800 | 2800 | 0
| Costume Supervisor | 1 | 5 | 600 | 3000 | 1000 | 1 | 600 | 600 | 200 | 4800 | 4800 | 0 | Present for all rehearsal weeks, tech week and 1 more week to cover prep
| Wigs Supervisor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wardrobe Maintenance / Dresser | 2 | 1 | 450 | 900 | 0 | 2 | 450 | 1800 | 0 | 2700 | 2700 | 0 | LA increased to 2 people. Will we need washing separate due to hours? Likely to be lots due to community cast. Assume local person
| Crew / Instrument tech | 1 | 1 | 450 | 450 | 0 | 2 | 450 | 900 | 0 | 1350 | 1350 | 0 | 1 Crew; 1 addition ASM / Tech added; Assume local person
| Tech Staff Overtime |  | 8% |  | 1004 |  |  | 5% | 275 |  | 1279 | 1279 | 0 | ADDED FULL TEAM
| Tech Staff NI |  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | NI not applicable
| Production Team Travel | 12 |  | 90 |  | 1080 |  | 90 |  | 1080 | 2160 | 2160 | 0
| Production Team Expenses | 12 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| SUB TOTAL |  |  |  | 25487.3333 | 8080 |  |  | 10428.3333 | 3680 | 47675.6667 | 47675.6667 | 0
[10 empty] | CHECK | 47675.6667 |  | 47675.6667
| TOTAL CREATIVE TEAM, PRODUCTION & CONSULTANTS | [9 empty] | 131626.1067 | 119525.6667 | 12100.44
ZK104 - PERFORMERS AND MUSICIANS | [10 empty] | BUDGET | FORECAST | DIFFERENCE | NOTES
Sub code | Details | Rehearsals |  |  |  |  | Running | [6 empty] | Including Sunday payments
| Performers Salaries | Number Artists | Number Weeks | Weekly Salary | Total Salary | Subs | Weeks | Weekly Salary | Total Salary | Subs |  |  |  | 7 show week
| Actors | 8 | 5 | 500 | 20000 | 8000 | 2 | 500 | 8000 | 3200 | 39200 | 39200 | 0 | Inclusive instrument hire
| Understudies | 0 | 5 | 60 | 0 | 0 | 2 | 60 | 0 | 0 | 0 | 0 | 0
| Dance Captain | 1 | 5 | 37 | 185 | 1000 | 2 | 37 | 74 | 74 | 1333 | 1333 | 0
| Company Overtime |  | 8% |  | 1614.8 |  |  | 5% | 403.7 |  | 2018.5 | 2018.5 | 0
| Company NI |  | 13.8% |  |  |  |  | 13.8% |  |  | 0 | 0 | 0 | NI not applicable
| Company Holiday Pay |  | 8.333% |  | 1682.0833 |  |  | 8.333% | 672.8333 |  | 2354.9167 | 2354.9167 | 0
| Company Pensions |  | 3% |  | 605.55 |  |  | 3% | 242.22 |  | 847.77 | 847.77 | 0
| Company Medical Costs | 8 | 5 | 10 | 400 |  | 2 | 10 | 160 |  | 560 | 560 | 0
| Company Travel/Misc | 8 |  | 90 | 720 |  |  | 90 | 720 |  | 1440 | 1440 | 0
| Totals Company Costs |  |  |  | 25207.4333 | 9000 |  |  | 10272.7533 | 3274 | 47754.1867 | 47754.1867 | 0
| Musicians | 6 | 3 | 500 | 9000 | 3600 | 2 | 500 | 6000 | 2400 | 21000 | 0 | 21000 | LA REMOVED DUE TO BUYOUT ABOVE
| Musicians Overtime |  | 8% |  | 720 |  |  | 5% | 300 |  | 1020 | 0 | 1020
| Musicians NI |  | 13.8% |  |  |  |  | 13.8% |  |  | 0 | 0 | 0
| Musicians Holiday Pay |  | 8.333% |  | 750 |  |  | 8.333% | 500 |  | 1250 | 0 | 1250
| Musicians Pensions |  | 3% |  | 270 |  |  | 3% | 180 |  | 450 | 0 | 450
| Musicians Travel | 6 |  | 90 | 540 |  | 2 | 90 | 540 |  | 1080 | 0 | 1080
| Musicians Porterage | 6 |  | 50 | 300 |  | 2 | 50 | 100 |  | 400 | 0 | 400
| Total Musicians Costs |  |  |  | 11580 | 3600 |  |  | 7620 | 2400 | 25200 | 0 | 25200
| SUB TOTAL |  |  |  | 11580 | 3600 |  |  | 7620 | 2400 | 25200 | 0 | 25200
| Performer Fees | [9 empty] | 35480.1867 | 35480.1867 | 0
| SUB TOTAL | [9 empty] | 35480.1867 | 35480.1867 | 0
| Performer Expenses | [9 empty] | 12274 | 12274 | 0
| SUB TOTAL | [9 empty] | 12274 | 12274 | 0
| Musician Fees | [9 empty] | 19200 | 0 | 19200 | REMOVED MUSICIAN DUE TO BUYOUT
| SUB TOTAL | [9 empty] | 19200 | 0 | 19200
| Musician Expenses | [9 empty] | 6000 | 0 | 6000
| SUB TOTAL | [9 empty] | 6000 | 0 | 6000
| TOTAL PERFORMERS & MUSICIANS | [9 empty] | 72954.1867 | 47754.1867 | 25200
ZK105 - REHEARSAL COSTS | [10 empty] | BUDGET | FORECAST | DIFFERENCE
[11 empty] | BUDGET | FORECAST
| Rehearsal venue | [9 empty] | 2000 | 2000 | 0 | Assume MRE space provided without cost for Manchester rehearsals; Hull space required for community and full rehearsals
| SUB TOTAL | [9 empty] | 2000 | 2000 | 0
Rehearsal set-up costs
| Scripts & Photocopying | [9 empty] | 250 | 250 | 0
| Music Copying & Orchestration costs | [9 empty] | 1000 | 1000 | 0
| Model Box Costs | [9 empty] | 500 | 500 | 0
| SUB TOTAL | [9 empty] | 1250 | 1250 | 0
Rehearsal running costs
| Rehearsal costs | [9 empty] | 1000 | 1000 | 0 | LA increased from £500 to include rehearsal set, steel deck, PA etc.
| SUB TOTAL | [9 empty] | 1000 | 1000 | 0
| Volunteer Cast Costs | [9 empty] | 500 | 500 | 0
| SUB TOTAL | [9 empty] | 500 | 500 | 0
| TOTAL REHEARSAL COSTS | [9 empty] | 4750 | 4750 | 0
ZK106 - TECHNICAL & PRODUCTION | [10 empty] | BUDGET | FORECAST | DIFFERENCE
Technical Stage
| TSM Materials | [9 empty] | 2000 | 2000 | 0
| Fit-Up | [9 empty] | 10000 | 10000 | 0
| Get-Out | to cover weekly changeovers | [8 empty] | 10000 | 10000 | 0
| Venue Preparation | dressing rooms, box office, company office, wifi etc | [8 empty] | 15000 | 15000 | 0
| Transport costs | [9 empty] | 2000 | 2000 | 0
| SUB TOTAL | [9 empty] | 39000 | 39000 | 0
Costume & Wigs
| Wardrobe Materials | [9 empty] | 8000 | 8000 | 0
| Costume - running & hires | 200 | per running week | [7 empty] | 400 | 400 | 0
| SUB TOTAL | [9 empty] | 8400 | 8000 | 400
Set & Props
| Materials | [9 empty] | 7000 | 7000 | 0
| Props - running & hires | 200 | per running week | [7 empty] | 400 | 400 | 0
| SUB TOTAL | [9 empty] | 7400 | 7400 | 0
Lighting & AV
| Build materials | [9 empty] | 1000 | 1000 | 0
| LX & AV running & hires | 1000 | tech week plus per running week | [7 empty] | 3000 | 3000 | 0
| SUB TOTAL | [9 empty] | 4000 | 4000 | 0
| Audio & Comms | [12 empty] | To include radio mics, CANS, 6 Piece band, vocals, backline etc
| Build Materials | [9 empty] | 1000 | 1000 | 0
| Instrument maintenance | [9 empty] | 500 | 500 | 0
| Sound running & hires | 2500 | tech week plus per running week | [7 empty] | 7500 | 7500 | 0
| SUB TOTAL | [9 empty] | 9000 | 9000 | 0
| Rigging | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Power & Generators | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Pyrotechnics | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| TOTAL TECHNICAL & PRODUCTION | [9 empty] | 67800 | 67400 | 400 | Includes running physical
ZK107 - VENUE & LOGISTICS | [10 empty] | BUDGET | FORECAST | DIFFERENCE
Venue costs
| Audition costs | [9 empty] | 1000 | 1000 | 0
| Venue fees | [9 empty] | 10000 | 10000 | 0 | Requires Guildhall to be 'provided' for reduced hire and basic costs
| SUB TOTAL | [9 empty] | 11000 | 11000 | 0
| Comms Equipment | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Production Transport | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Temporary Buildings | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Temporary Structures | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Policing, Safety & Medical | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Cleaning & Waste | [9 empty] | 0 | 0 | 0 | LA included in venue costs
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Plant Hire | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
Site Prep & Security
| FOH Attendants / Security | 6 @ £50 per perf; plus 1 session prep | [8 empty] | 4500 | 4500 | 0
| FOH Fireman / First Aid | £50 per perf; plus 1 session prep | [8 empty] | 750 | 750 | 0
| FOH MANAGER | 1 @ £75 per perf, plus 3 sessions prep | [8 empty] | 1275 | 1275 | 0
| BOX OFFICE Staff | 2 @ £75 per perf | [8 empty] | 2100 | 2100 | 0
| TOTAL | [9 empty] | 8625 | 8625 | 0
| TOTAL VENUE & LOGISTICS | [9 empty] | 19625 | 19625 | 0
ZK108 - PROGRAMME LEGAL & DOCUMENTATION | [10 empty] | BUDGET | FORECAST | DIFFERENCE
Legal
| Insurance | [9 empty] | 3500 | 3500 | 0 | Venue insurance for found space & all kit, instruments etc
| SUB TOTAL | [9 empty] | 3500 | 3500 | 0
| Documentation | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| TOTAL PROGRAMME LEGAL & DOCUMENTATION | [9 empty] | 3500 | 3500 | 0
ZK109 - PROGRAMME MARKETING, DIGITAL & COMMS | [10 empty] | BUDGET | FORECAST | DIFFERENCE
Branding & Design
| Marketing costs | [9 empty] | 15000 | 15000 | 0
| SUB TOTAL | [9 empty] | 15000 | 15000 | 0
| Distribution Costs | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Print Costs | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Photography | inc image generation | [8 empty] | 2500 | 2500 | 0
| SUB TOTAL | [9 empty] | 2500 | 2500 | 0
| Filming | [9 empty] | 500 | 500 | 0 | LA inserted as we will want an archive of the show.
| SUB TOTAL | [9 empty] | 500 | 500 | 0
| Digital Content Creation | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Web Development | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
0
| Evaluation & Research | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| TOTAL PROGRAMME MARKETING, DIGITAL & COMMS | [9 empty] | 18000 | 18000 | 0
ZK110 - PROGRAMME EDUCATION & COMMUNITY ENGAGEMENT | [10 empty] | BUDGET | FORECAST | DIFFERENCE
Engagement Events
| Education resources | [9 empty] | 1500 | 1500 | 0
| SUB TOTAL | [9 empty] | 1500 | 1500 | 0
| School Activity | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Public Programming | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
Access Initiatives
| Interpreted Performances | [9 empty] | 800 | 800 | 0
| SUB TOTAL | [9 empty] | 800 | 800 | 0
| Participation Workshops | [9 empty] | 0 | 0 | 0
| SUB TOTALS | [9 empty] | 0 | 0 | 0
| Community Cast | [9 empty] | 4200 | 4200 | 0 | £10 per perf for 30 community cast
| SUB TOTAL | [9 empty] | 4200 | 4200 | 0
| TOTAL PROGRAMME, EDUCATION & COMMUNITY | [9 empty] | 6500 | 6500 | 0
ZK111 - PROGRAMME VOLUNTEERING | [10 empty] | BUDGET | FORECAST | DIFFERENCE
| PPE | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Costume & Wigs | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| External Training | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Volunteer Co-ordinator | 1 @ £75 per show | [8 empty] | 1050 | 1050 | 0 | LA inserted. Based on 1 FOH (including volunteering) & 2 BO. This might still be too low?
| SUB TOTAL | [9 empty] | 1050 | 1050 | 0
| DBS Checks | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| TOTAL PROGRAMME VOLUNTEERING | [9 empty] | 1050 | 1050 | 0
ZK112 - ARTIST & GUEST LIAISON | [10 empty] | BUDGET | FORECAST | DIFFERENCE
| Accreditation | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| HLT Costs | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| VIP Guests | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Catering | Press Night | [8 empty] | 500 | 500 | 0
| Green Room Facilities | [9 empty] | 1000 | 1000 | 0
| SUB TOTAL | [9 empty] | 1500 | 1500 | 0
| Media Guests | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| TOTAL ARTIST & GUEST LIAISON | [9 empty] | 1500 | 1500 | 0
ZK113 - RUNNING COSTS | [10 empty] | BUDGET | FORECAST | DIFFERENCE
| Venue Extension Running Costs | [9 empty] | 0 | 0 | 0
| SUB TOTALS | [9 empty] | 0 | 0 | 0
| Weekly Extension Wages Costs | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| Weekly Extension Running Costs | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| TOTAL RUNNING COSTS | [9 empty] | 0 | 0 | 0
ZK114 - ADMIN & MISC | [10 empty] | BUDGET | FORECAST | DIFFERENCE
| Admin Costs | [9 empty] | 0 | 0 | 0
| Producer Costs | [9 empty] | 500 | 500 | 0 | LA increased due to rehearsals in Manchester; reduced as provision in R&D costs
| SUB TOTAL | [9 empty] | 500 | 500 | 0
| Equipment & Tools | [9 empty] | 0 | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0 | 0
| TOTAL ADMIN & MISC | [9 empty] | 500 | 500 | 0
TOTAL COSTS OF THE PRODUCTION | [10 empty] | 335827.2933 | 334126.8533 | 1700.44
Note on B120: Alvisl: Covered by SF
Note on D162: Alvisl: Includes tech