| Name of Individual / Organisation | Priory Primary School – Julia Mitchell and Louisa Waldron |
| --- | --- |
| Name of Project | The People of Priory Festival |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

| START DATE | END DATE | ACTIVITY / TASK | STATUS | NOTES |
| --- | --- | --- | --- | --- |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| September 2016 | December 2016 | - Staff Meeting – initial ideas regarding genre of art to be explored - Recruit ‘artists’ to lead workshops within the school (musicians/sculpture/art/dance) - Children to create a pitch for local business/community groups to commit to the event - Hiring of event facilities (stage ect..) | Complete Complete Behind Stage hired other facilities to do |  |
| January 2017 | March 2017 | - Various planning meetings for timetabling / roles for the event / safety - A review of local business interests - Website completed –www.peopleofpriory.co.uk - Classes within the school starting to work with artists to create artwork to sell. | Ontime, ongoing. Met with Council team and Event guided started Behind Facebook page up and running Dates set |  |
| March 2017 | June 2017 | - Children continue to work with artists to create their pieces of art. - May 2017 a final list of businesses, artists, community groups confirmed. - May 2017 – final line up for the main stage. - Sculpture to be in the developing stages - Flyers to be created but not distributed. - Social media to be set up Twitter/ website |  |  |
| May 2017 | July 2017 | - Marketing – all forms and increasing in intensity towards the final date - Allocations of roles within the staff and community for the day - Final plans and timetabling - Confirmations and contracts finalised. - Rehearsal for groups within the school |  |  |
|  | Saturday July 8th 2017 | The People of Priory Festival |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances