Turner Prize Events Meeting
05.10.2017

Katy Fuller, Jenny Hutt, Lily Mellor, Rebecca Clark

Apologies: Chris Clay, Liz Draper, Ben McKnight

1. Review of Opening Event

- JH to send estimate to corkage costs to KF

- 451 guests attended on 25.09

- Feedback from Tate – everyone very happy, including patrons

2. Stakeholder Events

- Ernst & Young, timing issue

- KCOM Private View on Tuesday 10th October

3. Guest list & Invite

- Design of the invite TBC - Line specifying personal, single and non-transferrable invitation - LM to feedback to LS

- LM confirmed GF Smith are printing them

- Wristbands for dinner guests & staff to be decided

- Invite list to be finalised, JH to invite Hull 2017 board

- Invite to go out on 20 October. RSVP deadline – 10/11/2017 
Date for second tranche TBC

- Drinks reception for the Artists on Mezzanine at Ferens TBC

4. Schedule

- 05/12/2017 - Ferens confirmed closure

- BBC to rig Minster on Monday 4 December, rig Ferens on Tuesday 5 December

- KF to confirm BBC access timings at Ferens to rig

- RC to pull together a schedule

- Guests to privately view exhibition 18:30-19:30 prior to presentation at Minster

5. Venue

- KF to confirm whether Ferens and Minster exterior can be lit 05/12

HPSS up lighting easy to arrange.

- KF to confirm times and location for Jury to access Ferens for deliberation

- LM to investigate location for Jury -  offices at Ferens / Volunteer Room / Education room / Maxine’s office / Room availability at Maritime Museum / Committee Room at Hull City Hall

- RC to arrange luxury portaloos near the Minster

6. Artists & Green Rooms

- Goldie relationship to be managed by KF. 
2 x rooms to be held at the Hideout for Goldie (green room)

- JH confirmed 4 x artists booked to stay at Holiday Inn Marina