PRSF NEW MUSIC BIENNIAL

HULL

29th JUNE to 2nd JULY 2017

ARTIST PACK

ARTIST: Sam Lee

ARTIST CONTACT (Mobile number): TBC – PROMOTER TO CONFIRM

VENUE: Hull Minster

Address: Market Pl, Hull HU1 1RR, UK

Phone: +44 1482 224460

LOADING IN FROM: North Church side, (Purple P)

PARKING REQUIREMENT and LOCATION:

TBC – PROMOTER TO CONFIRM

PERSONNEL

STAGE MANAGER (Primary contact show weekend only): Ben Pugh - 07970 950552

PRODUCTION MANAGER: Gareth Hughes – 07733112272

PRODUCTION ASSISTANT: Joanna Morley – 07725 942808

VENUE CONTACT: Jane Owen

DATE AND TIME OF PERFORMANCE: Sunday 2nd July 20:00 (45mins)

PRODUCTION SCHEDULE:

| FRIDAY 30 JUNE |  |  |  |
| --- | --- | --- | --- |
| 08:00 - 00:00 (ACCESS) | 09:00 - 16:00 | Sound in | HPSS |
|  | 13:00 - 20:00 | Daniel Elms - rehearsal | Dan Elms |
|  | 21:00 | Box office on site | David Watson |
|  | 21:45 | Doors | SM |
|  | 22:15 | Daniel Elms - PERFORMANCE | Dan Elms |
|  | 23:00 | Finish | SM |
|  | 00:00 | Cleared - SL/SR screens derigged | HPSS |
| SATURDAY 1 JULY |  |  |  |
| 20:30 | Piano delivered | From Fruit |  |
| SUNDAY 2 JULY |  |  |  |
| 08:00 - 00:00 (ACCESS) | 09:00 - 12:00 | Risers configured for Peter Edwards brass | HPSS |
|  | AM | Piano tuned | ??? |
|  | 12:15 - 13:00 | Artists arrive - Peter Edwards | Peter Edwards |
|  | 13:00 - 15:45 | Rehearsal - Peter Edwards | Peter Edwards |
|  | 15:45 | Doors | FOH |
|  | 16:15 | PERFORMANCE - Peter Edwards | Peter Edwards |
|  | ??? Sam Lee |  |  |
|  | ??? Sam Lee |  |  |
|  | 19:30 | Doors | FOH |
|  | 20:00 | PERFORMANCE - Sam Lee | Sam Lee |
|  | 21:30 | Cleared | FOH |
|  | 21:30 - 00:00 | LX and sound out | HPSS |
| MONDAY 3 JULY |  |  |  |
| 08:00 - 12:00 (ACCESS) | 08:00 - 12:00 | Staging out | HPSS |
|  | AM | Piano out | ??? |

TECHNICAL

Sound

FOH Control

1 Yamaha LS9-32

Speaker System

6 L Acoustics - KARA

4 L Acoustics - KARA-ANGARMEX

2 L Acoustics - KARA M-Bump

2 L Acoustics - SB18

2 L Acoustics LA8

Monitor System

2 L Acoustic 108P

2 Rane 4 Channel Headphone Amplifier

8 Sennheiser HD201 Headphones

10 6.35mm Headphone Extension Cable

Microphones

4 Shure SM58

4 Microphone Stand - Tall

3 d:vote DPA 4099

2 DPA Clip for Piano (PC4099)

1 DPA Clip for Sax and Trumpet (STC4099)

3 DPA DAD 6001 XLR 48 volt adapter

1 Sennheiser e906

1 Microphone Stand - Short

Other Equipment

1 63A 3-Phase Mains Distro #3

1 63A 1-Phase Cable 10m

Staff

1 Engineer - FOH

1 Local Crew

1 Local Crew

AV

Projection

1 Truss Hammer

1 Christie Lens ILS 0.73SX+/0.67HD

1 Christie Roadster HD20K- J Series Projector

1 8m x 4.5m Contrast Grey Projection Surface (Widescreen)

4 Litec QX30 - Corner Dado Section

2 Litec QX30S - 0.5m Truss Section

2 Litec QX30S - 1m Truss Section

4 Litec QX30S - 2m Truss Section

6 Litec QX30S - 3m Truss section

32 Litec QX30S - Spigot

128 Litec QX30S - Split Pin

128 Litec QX30S - Truss Pin

2 Geni Super Lift

1 Custom Screen Surround

Sources

1 Apple iMac 21.5"

Processing

1 Black Magic ATEM 1 M/E Production Studio 4K

2 Black Magic Mini Converter - HDMI to SDI 4k

2 Black Magic - Switching PSU for Mini Convertor

Staff

1 Engineer – AV

Lighting

Control

1 Avolites Tiger Touch Pro Console

1 Avolites PowerCube

1 100m Lighting Multicore

Fixtures

4 Alu LED Par RGBW 18x 8W - 40deg

6 Robe Pointe

6 Robe Robin 600 LED Wash

6 ETC Source Four Junior Zoom 25 - 50 Degree

12 Prolights SmartBat+

Rigging

2 Litec QX30S - 3m Truss section

Misc

1 63A 3-Phase Cable 23m

Transportation

1 7.5T Box Van

1 Engineer - Lighting

1 Lighting Tech

RIDER:

BACKLINE:

ACCREDITATION

David & Alice Porter (Directors)

Steve & Sam Shaw (Directors)

Peter & Lorraine Boardman (Directors)

Wes Zepherin (Director)

Kirsty & Gary Halliday (Marketing)

Ben Pugh (Production)