- COUM Transmissions

- Production delivery Plan and responsibilities of Hull 2017

    - have the right to review the Production and, where further development of the Production is required, shall allow the Producer a further reasonable period of time to develop the Production and resubmit the Production proposals to Hull 2017 for approval;

    - liaise with Producer on a regular basis and assist Producer in ensuring the success of the Production as an ongoing process

    - where relevant advise on matters relating to UK City of Culture including transportation, security, marketing and other related logistic and production issues

    - provide funding to effect the Production in accordance with Section 2 of this Agreement;

    - Assist Producer with the mitigation of any risks relating to the Production.

    - Provide the venue for the Production and such other production deliverables such as exhibition furniture, plinths, and vitrines where necessary.

    - Cover all insurance requirements

Timelines

- The producers contracted – W/C 18 July 2016

- Archiving commences – W/C 18 July 2016

- Live artists and new commissions contracted w/c 12 august 2016

- Writers commissioned W/C 12 September 2016

- Press launch – 22 September 2016

- Exhibition plan/ exhibition content agreed – W/C 24 October 2016

- Publication finalised and to print W/C 28th Nov

- Install W/C 16 – 31 January 2017

- Exhibition Open and Opening event 3 February 2017