Larkin Exhibition

Monday 26 September 2016

Present: SW, CS, GC, PP, HWW

Apologies: MLS

Notes: HWW

NOTES

Marketing Copy and Image

The Hull 2017 brochure for season 3 and 4 is due to come out in February which means we will need copy about the exhibition in November.

We will also need an image for the brochure. It was suggested by the group that we look at Larkins doodles, self-portraits and photo archive.

Action: SW to bring images to the next meeting.

Action: CS/HWW to confirm marketing deadline.

Exhibition Title

The exhibition needs a title for the November deadline. CS suggested we look for words or phrases that were used by Larkin in his work.  GC suggested a different resonance.

Action: Everyone to come to the next meeting with suggestions.

Curator

There was a group consensus to move away from a celebrity curator and focus on events within the programme where we can invite celebrity guests.

PP suggested Mark Lawson for a talk.

CS met with Anna Farthing. She has a background in developing exhibitions and recently did an exhibition about Agatha Christie. The group decided it would be useful to meet her as a potential curator and the date of the 27th of October was suggested for a tour of the History Centre and the University.

Action: CS to circulate Anna’s CV

Action: HWW to confirm the date Anna will visit.

Action: CS/HWW to check procurement processes.

Grayson Perry Lecture

The Larkin society has confirmed that Grayson Perry will deliver the annual Larkin lecture at Middleton Hall on 5th July 2017.

A save the date has been sent to all members of the Larkin society.

Marketing and Comms

The group spoke about a need to tell the story of Larkin next year and join up the various events that are taking place. Including the unveiling of the Larkin memorial stone at Westminster Abbey and the Grayson Perry lecture and exhibition.

Action: HWW to set up a marketing meeting on the 27th October to discuss.

Artist Commissions

Martin Green suggested the idea of commissioning five artists to respond to Larkins archive rather than have a curator.

The group liked the idea of artists responding to Larkins work but felt there had been exhibitions that had done this before and would prefer to have a curated exhibition as there isn’t the budget to do both.

SW mentioned that Heritage lottery have a new fund open which we could encourage local artists to apply to for 2018. It was suggested that support for this could be announced with the programme.

Exhibition Design

Action: CS and SW to look and see what is in the budget before the group look into this.

BBC

Action Simon to contact TV Producer Christine Hammill, making the documentary to get an update.