RIBA/LOOK UP 2017 COMPETITION

Draft Outline Programme v2 010716

2016	Organisation & Brief

Agree responsibilities & budget by	29 July

Agree brief & programme by 		26 Aug

Competition Launch/Competitor Selection

EOI Invitation & Outline Brief issued:12 Sept (3 weeks) – up to x practices

RFC’s by				23 Sept

EOIs submitted by:			30 Sept

EOIs reviewed/final shortlist w/c	02 Oct

Competition Invitation issued		09 Oct (3 practices)

Competition

Competitor Site Visits w/c		17 Oct

2017	Competition submissions		09 Jan

Presentations & Review w/c		09 Jan

Winner Announced			17 Jan

Detail Design & Consents

Detail Design				23 Jan – 24 Feb (5 weeks)

Consents				20 Jan – 21 April (8 weeks)

Fabrication/Installation

Fabrication				24April – 11 Aug (16 weeks)

Installation				14 – 23 Aug

Launch					24 Aug

Freedom Festival			1-4 Sept

On Site

On site 				25 Aug – 27 Oct (8 weeks)

EOIs to include statement re approach to architect/artist collaboration, named lead designers, practice cv’s, 500 word statement ‘what we want to do’

Review Panel to include 2 or 3 ‘advisors’, comment through process and judge final submissions

Submissions to include model to common scale, visuals, material samples, written description and outline costings (to assess reasonable degree of aesthetic, cost, programme & technical feasibility)

Period covers launch of Turner Prize exhibition