LARKIN Meeting – 20 December 2016

My questions:

How do I access the archive when Simon isn’t available?

Copies of AV material?

Draft  Cooperation Agreement is ready from Hull 2017

A gathering of everyone’s schedule and pinch points: by 10th January

Cooperation Agreement - Partner Credits:

Hull 2017

Philip Larkin Society

University of Hull

PLS – Philip and Graham

University – Simon (archives) and Marianne (venue – may be devolved to manager of exhibition space)

Head of customer services at the library (Ali Craig)

Glen Burgess – acting VC of Hull

AF ACTION: GO TO THE GALLERY – See the British Museum exhibition

Dates: 1st July is a Saturday – bad date to open – too much happening – not good to invite people.  Could open with a PV on Tuesday 4th July  (who do we want to open it) 5th July open to the public (Grayson is 5th)  He arrives on the Wednesday at midday – wants to see the exhibition.

I suggest we do the build up to Friday

Weekend OFF

I want to do Audience Testing on the Monday

CHECK THIS ACTION PLS to do an introduction of Anna to Grayson

Anna will have a chat about any content he might wish to contribute

Meeting between University Comms Team with City of Culture

11th January – an internal meeting to explain ways of working and timescales.

Get these dates into our big schedule. Hannah to hold that document as she has the broader Hull 2017 dates.

Doodles are owned by the estate

Copywright is held by Society of Authors

Poetry workbooks of final drafts are Faber

Sketch drafts with scribblings is Society of Authors

Previously unpublished

DLV Larkin photographic series

Self portrait in contact sheet

Why NOT use the Doodles

He originally drew himself as a fish and a seal

Big, clumsy, lumpy, unattractive.

Doodle is an act of self presentation

MUST CHOOSE IT THIS AFTERNOON

No one is currently working on the doodles as a research project.

Negs of images he shot are in the archive – so we could create a contact sheet from some of those.

University uses Hull Box Office, as does Hull 2017.

Private tickets for PLS members to get Grayson event

Get a link etc.

Middleton Hall – ticketed seating not unreserved.

The Westminster Event

Alan Bennett declined to do the address (too busy) but talks about Larkin all the time.  If we make it easy for him he might do it

Tom Courteney – from Hull

Edward Fox  there as guest of Martin Jennings

Melvyn Bragg

AN Wilson

DS, TC and MB are both Vice Presidents of PLS

Tom Stoppard is also a VP of the PLS

Virginia Bottomley was also there

Everyone wanted to talk to Grayson Perry said – they are all of a certain age

Rosemary Parry – Larkin’s neice

Dale Salwak – American academic

Simon says:

There will be a world exclusive premier of a MUSIC RECORDING event

The weekend after we open

A concert at the University is planned

Home is So Sad – put to music to David Dubery in the 1980s

Couldn’t get the permissions from Faber – now have permission for it to be performed – friends with James Gilchrist the Tenor – will be performed by the chamber ensemble. Classical music composition.

Last year there was an event on Larkin’s Birthday

Dave Gorthorp – local bands – hillbilly troupe – also made music videos

A film on Youtube – Vimeo

Philip has the link GET IT

University compositions

Legacy and impact element:

Artefacts should be labeled as belonging to the PLS (not mention that its held in the History Centre)

There are three main repositories of the artefacts

- History Centre – mostly owned by PLS

- University – Librarians Office stuff  owned by the university

- James Booth – personal collection of Larkinalia owned by PLS (lives in Hull)

Larkin Society Materials are in the archive but not properly catalogued

NEED ACCESS TO THE BOX

Weight

A letter of the speak my weight machine ticket

Where is the booklet of weights from two sets of scales

Things that speak rather than tell people stuff

Larkin doesn’t care about his appearance

Evidence to the contrary

A miserable man

Very funny

Parents fuck you up

He had a great relationship with his mother

Contradictions

Myth busting

Date and thematic focus of next meeting:

History Centre to look at archives and objects

University to look at space