Appreciation of Task

The meeting was very helpful to understand the requirements of the Feasibility Study and to be able to discuss key considerations moving forward. The key questions that the Feasibility Study is expected to answer are:

- Is it possible to transport a 75m wind turbine blade from Alexandra Dock such that it can be situated in a city centre location (to be agreed) for 12 weeks?

- Where are the viable locations in the city centre?

- What arrangements/consents will be required?

- How can the blade be displayed (including alignment, maintenance, security and  H&S)?

- What scale of costs are likely to be incurred?

- What would be the most effective management/governance structure to deliver this  installation?

- How will it be disposed/removed?  Arup will be expected to collaborate with Hull UK City of Culture 2017, Nayan Kulkarni and Hull City Council (including the Public Realm team) in order to address the questions posed above.  We understand that we will also need to liaise with Siemens to understand the technical specification of the “decommissioned” blade and the conditions in which it is being offered, and may have to be returned. A meeting has been arranged with Siemens on Wednesday 4th May 2016 and my colleague Javed Hussain has already confirmed his attendance.

Arup will commission the services of a haulier to provide specialist advice relating to the transport of abnormal loads in order to identify route choice, impact on infrastructure, escorting and permit requirements, structural constraints and the type of vehicle to be able to transport the blade. The specialist haulier will only provide advice in a consultancy role with no exclusivity offered to the haulier for subsequent phases of the project therefore not restricting any future tendering process.

The study would help to establish who should take responsibility for the blade whilst “on site”, how this risk can be mitigated/minimised.

The Feasibility Study will provide a cost estimate of the overall works in considering the preparation, installation, transport, operation and removal for the Zephyr installation. A programme will also be provided.

We understand that we will need to sign a Non-Disclosure Agreement in recognition of the confidential nature of the scheme and we are happy to do so.

Scope of Services

Considering the above and the discussions to date, we anticipate the following to form our scope of works to prepare a Feasibility Study:

- Collaborate/liaise with Hull UK City of Culture 2017, Nayan Kulkarni, Hull City Council and Siemens.

- Work with Nayan Kulkarni to identify locations for positioning the art piece and agree a preferred location with the project team.

- Identify route(s) to transport the Zephyr from Queen Alexandra Docks to the agreed location. The route(s) will be visited and a route access survey will be undertaken to either discount the assessed route or identify the impact on infrastructure.

- Identify alterations required within the highway (including temporary removal of furniture, signage, etc) in order to deliver and remove the art piece.

- Attend up to 6 meetings/workshops/site visits as required (see under heading for meetings/workshops below).

- Prepare a general arrangement drawing showing the agreed position and setup arrangements. This drawing will also show safe working zone and operational space.

- Prepare a Risk Register.

- Prepare a Cost Estimate based on the findings of the study.

- Summarise the above findings in a report for submission to Hull UK City of  Culture 2017 in electronic format (PDF).  For the avoidance of doubt, please note the following specific exclusions from this proposal:

  - Design (i.e. for lighting, water, power, etc.), procurement, planning support, etc, have been excluded from the current scope/fee as the requirements for such is dependent upon the Artists requirements which are unknown at this stage.

  - Structural assessment of the blade/art piece and its supports to verify integrity – we expect Siemens to provide this information.

Deliverable

The deliverable of this project is a Feasibility Study report which comprises:

- Brief overview of Working Constraints and site selection

- General arrangement drawing for agreed location

- Preferred transport route(s) for delivery and removal of art piece

- Cost Estimate including budget costs for street works and transport

- Risk Register

- Outline programme

- Next Steps

- Arup Team

Page 3 of 6

Richard Bickers leads Arup’s Consulting business in the North West, Yorkshire and The Humber and is currently responsible for delivering the design of the Hull Public Realm improvements. Richard will be the Project Director for this commission and will be responsible for agreeing the terms of reference for the study and for ensuring that the project delivers against these requirements. He would be the high level contact with Hull 2017 regarding any concerns they may have about the project’s progress, or contractual or budgetary issues.

The feasibility study will be led by Javed Hussain who is a Senior Engineer within Arup’s Transport Consulting team based in Leeds. Javed will be your main contact and be responsible for the day to day running of the project. Javed led the transport work for the Hull Public Realm scheme and worked with Hull City Council’s Major Projects Team and Streetscene to agree the transport strategy.

Input will be drawn from other Arup staff as and when required. This will be required for preparing the Risk Register and Cost Estimate, and for advising on the management/governance structure.

Attendance at Meetings, Workshops and Site Visits

Our fee allows for attendance at the meeting with Siemens on 4th May 2016 in Hull and for a further 5 meetings, workshops or site visits in Hull.

Programme

Based on our discussions to date, the following table sets outs out the anticipated timescales for the feasibility work.

Page 4 of 6

| Programme Stage | Timescales |
| --- | --- |
| Identify position of Zephyr, potential delivery routes and agree preferred location | 2 weeks |
| Assess route(s) and liaison with HCC Highways. | 3 weeks |
| Liaise with HCC to confirm permit, licence and consent requirements. “Ownership” will also be considered at this stage. | 3 weeks |
| Prepare Cost Estimate and Risk Register | 2 week |
| Prepare and issue Feasibility Study | 1 week |

Indicative Programme

Some of the work identified in the above table can be undertaken concurrently and therefore we estimate a programme period of 6 – 8 weeks to complete the feasibility work.