Turner // Return

Meeting Room 1

25/10/2017

Katy Fuller, Ian Read, Lily Mellor, Claire Drury, George Vasey, Rebecca Clark

- Hack & Host - Blue Box
Situated outside the gallery, in front of the Ferens
Run a café style workshop – handing out newspapers, sweets

RC to ask Aidan about battery flood lights
IR/LM to sign off Zine
IR to confirm location for Blue Box with Rachel at Hack & Host

- Entrance
No side entrance alternative now
Couple of volunteers in every room (30 in total) GV specified there are usually 20 in the building during the exhibition opening hours.

LM/CD to take into account Volunteer breaks

- Central Court
Exchange tours will set off from Central Court. Tours are still being developed 
7 teachers – group tours or individual tours tbc

IR to set times/liaise with teachers to decide timings

- Gallery 2
Future Ferens facilitating this activity
Anna Bean does participatory activities and giving food to people
Food to be managed by volunteers

IR/CD to send dimensions of trestles tables to be sent to Anna Bean
LM to ask Shaun to borrow Ferens trestle tables
CD to meet with HCAL catering / try and use another caterer

- Cloakroom
Run as we did in the opening

RC to book clothes rails out with Volunteering

- Studio

7.1 Curator talk 18:30 – 19:30 (inc. Q&A)

Pre-set questions to discuss. SC to chair it and GV to speak from the position of Turner Prize. GV to pose some questions to Sarah Munro and Ben Borthwick. 30 minute talk, and open up to Q&A.

Images behind speakers on large screen, chairs, tables, water.
Specific audience – check wording on website “Booking Advisable”
Capacity 150 seated

GV to speak to SC about the talk
RC to get 2 x lapel mics from HPSS
LM to request for Matt Lund to be there

7.2 Hull Independent Cinema Screenings 20:00 – 22:00

GV – Films of previous Turner Prize nominees, GV would be able to facilitate
GV – to ask Kirsten about the films in the Ferens Collection

LM to speak to Ellie at HIC
IR/CD to create a listings of films

- Gallery 3
Barbering – trimmed or styled by Greasy Fingers (tbc)
David the Turner Prize Supervisor used to be a barber

CD to confirm with KS the amount of water allowed
CD to confirm participation of Greasy Fingers

- Gallery 5 / Gallery 8 
Locus Dance creating pieces in response to visitors to the gallery - focused in the centre of the room (G5 on benches and G8 on the spot) 
Dance is a brief intervention as opposed to a deliberate response to the artworks.

GV – suggested having a conversation with the artists out of courtesy

LM/CD/RC to test portable PA’s in the galleries before booking HPSS

- Café / Shop
Café is opened so people can purchase drinks/food - volunteers monitoring this to ensure nothing is consumed in restricted areas (namely G4)

Fandangoekid based in café / shop

RC to order tables for Fandangoekid to paste on

- Gallery 11 / Thomas Ferens Gift
Folk bands are not available, electronic bands have been suggested by Ellie.
Music changes look of the space?
Matt has LED lighting available to use in house at Ferens

CD/LM/RC to confirm capacity in G11
CD to confirm bar arrangements install time in G11 with KS

- Marketing 

Targeted marketing to HSAD, Warren, Hull Uni  
Not huge budget for print marketing – mainly digital

IR/LM/CD to confirm activities with marketing so we can begin to announce the programme online

LM to speak to Comms about a Press Release

IR/CD to ask Fandangoekid to create posters for TR with tagline