## Look Up gantt
HULL 2017 - "Look Up"
Indicative Outline Milestones
|  |  |  | 2016 | [12 empty] | 2017
[13 empty] | Made in Hull |  |  | Roots and Routes |  |  | Freedom |  |  | Tell the World
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
PROGRAMME DEVELOPMENT
Artist visits/briefing
Co commissioner agreements
Site consents
Outline Programme
Artist shortlist
Artist research
Artist outline proposals
Proposal development
Artists Detailed proposals
Programme finalised
PROGRAMME DELIVERY - INDICATIVE
Major installation
Major installation
Research/small scale
HSAD
GF Smith
RIBA
Major installation
Final piece
Other elements have no date as yet:
Deep
Yorkshire Sculpture Triangle
Reyjavik/Rotterdam
Wodijzko