| Name of Individual / Organisation | A Song for Hull by Hull Children’s University, Hull and East Yorkshire NHS Choir and HPSS Events Associates Ltd |
| --- | --- |
| Name of Project | A Song for Hull |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

| START DATE | END DATE | ACTIVITY / TASK | STATUS | NOTES |
| --- | --- | --- | --- | --- |
| June 2016 | June 2016 | Funders sourced Criteria and focus written in full | COMPLETED / ON-TIME / NOTES |  |
| July 2016 | August 2016 | Personnel researched and appointed Personnel contracted All venues chosen and confirmed Grant applications completed Costing completed Sponsor list completed Contingent venue researched Marketing and branding designed and created Sponsorship proposals created Sponsorship proposals issued School proposal created |  |  |
| September 2016 | December 2016 | Schools approached and recruited Music programme designed and compilation commenced Music sheets and backing tracks researched Choirs approached and recruited Local authority culture team approached with written proposal Social media created for communications Rehearsals in school to commence Musical director to create programme Schools and choirs to be in contact with Liaison co-ordinator Jonathan Ansell’s programme to be put in place Press and media coverage to commence |  |  |
| January 2017 | February 2017 | Rehearsals to continue School visits to be held and coordinated Sponsors to be finalised and contracted Ticket outlets to be arranged Tickets to go on sale Early release and VIP Guests to be invited Volunteers recruitment commences Caterers to be booked Security to be arranged and finalised Other manpower to be arranged Site crew to be agreed and arranged Sound and lighting to be discussed Technical crew to be briefed |  |  |
| March 2017 | July 2017 | Choir visits and rehearsals to continue Jonathan Ansell to visit Media and press campaign continues Lighting and sound to be designed Set to be designed to budget Draft production schedule to be produced Event management plan draft to be produced Technical crew to be briefed Ticket sales to continue to be promoted VIP booking to be ongoing ESAG meeting to be arranged Programme advertising sales to commence |  |  |
| August 2017 | August 2017 | Health and safety documents to be finalised and put in place Volunteers trained Jonathan Ansell to come for a second visit Second draft documents sent to ESAG Programme advertiser sales continue Media and sales ongoing |  |  |
| September 2017 | September 2017 | EMP to be finalised Group rehearsals to begin Radio interviews to be arranged Marketing ongoing Production schedule to be issued – final |  |  |
| October 2017 | October 2017 | Group rehearsals to be arranged Programmes design and print to be finalised |  |  |
| Show day |  | Production schedule to be followed Last rehearsal in situ |  |  |
| October 2017 |  | THE SHOW |  |  |
| Post show |  | Meetings and de brief Accounts and final account Evaluation and reporting Final report back to City of Culture |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances