## Sheet1
PEOPLE KEY
JL = Jack Lowe / EE = Eddie Elbourne / SM = Jade Hunter / HPSS = LX / Freelance = Sound / JM= Joanna Morley
CURIOUS DIRECTIVE: FROGMAN PRODUCTION SCHEDULE |  | Version 6
Date & Time | Activity | Who | Notes
Tuesday 17th October
11:00-12:00 | Internet Survey | KCOM
Monday 30th October
08:00-09:30 | Pipe and Drape Install | All Occasions | Blackout windows
09:00-12:00 | Van Run | JM
PM 12:30-16:30 | Internet Installation | KCOM | Actual time TBC
13:30-15:00 | Arrival and Load-in | EE and JL/HPSS/Freelancer/JM
14:00-18:00 | Put together final 18 chairs, cabling and amps | EE & Freelancer | At the side
15:30-19:00 | Control Position Set-up | JL
| AV set up | JL
| LX cable run / into desk | HPSS
| Continue Pipe and Drape | JM | Performance Area
16:00-17:00 | Rig LX | HPSS | Check for power surge on the rings.
16:30 | Internet VR check | JL | Get in touch with KCOM if not working
18:00-19:00 | Sound cable run | Freelancer / EE | Depending on EE progress.
Tuesday 31st October
10:00-13:00 | Roll out all rubber and sound connectors onto all 48 chairs | EE/HPSS/Freelancer/JM
| Floor lay | JL and EE
13:00-14:00 | Break | All
14:00-17:00 | Plot LX | JL and EE
14:00-17:00 | Troubleshoot chairs | HPSS/Freelancer/JM
Wednesday 1st November
10:00-12:00 | Final Sound checks | curious directive
12:00-13:00 | Cast Checks Tech | All | SM and Actor arrive around 12noon.
13:35 | Set up | curious directive | Duty tech required from 60 mins before show.
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 1 | curious directive
14:30 | End
18:35 | Duty Tech |  | Duty tech required from 60 mins before show.
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 2 | curious directive
20:30 | End
Thursday 2nd November
13:30 | Duty Tech and FOH Manager to Arrive
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 3 | curious directive
15:45 | End
18:35 | Duty Tech and FOH Manager to Arrive
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 4 | curious directive
20:45 | End
Friday 3rd November
13:30 | Duty Tech and FOH Manager to Arrive
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 3 | curious directive
15:45 | End
18:35 | Duty Tech and FOH Manager to Arrive
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 4 | curious directive
20:45 | End
Saturday 4th November
13:30 | Duty Tech and FOH Manager to Arrive
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 3 | curious directive
15:45 | End
18:35 | Duty Tech and FOH Manager to Arrive
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 4 | curious directive
20:45 | End
Sunday 5th November
13:30 | Duty Tech and FOH Manager to Arrive
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 3 | curious directive
15:45 | End
18:35 | Duty Tech and FOH Manager to Arrive
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 4 | curious directive
20:45 | End
Monday 6th November - No Shows
Tuesday 7th November
13:30 | Duty Tech and FOH Manager to Arrive
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 3 | curious directive
15:45 | End
18:35 | Duty Tech and FOH Manager to Arrive
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 4 | curious directive
20:45 | End
Wednesday 8th November
13:30 | Duty Tech and FOH Manager to Arrive
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 3 | curious directive
15:45 | End
18:35 | Duty Tech and FOH Manager to Arrive
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 4 | curious directive
20:45 | End
Thursday 9th November
13:30 | Duty Tech and FOH Manager to Arrive
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 3 | curious directive
15:45 | End
18:35 | Duty Tech and FOH Manager to Arrive
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 4 | curious directive
20:45 | End
Friday 10th November
13:30 | Duty Tech and FOH Manager to Arrive
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 3 | curious directive
15:45 | End
18:35 | Duty Tech and FOH Manager to Arrive
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 4 | curious directive
20:45 | End
Saturday 11th November
13:30 | Duty Tech and FOH Manager to Arrive
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 3 | curious directive
15:45 | End
18:35 | Duty Tech and FOH Manager to Arrive
19:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
19:30 | Show 4 | curious directive
20:45 | End
21:00 | Get Out | All