01/11/2017

Turner Prize Events Meeting

Katy Fuller, Jenny Hutt, Lily Mellor, Mike Berriman, Rebecca Clark, Ben McKnight, Chris Clay

- GUESTLIST

  - RSVP Responses
34 Yes RSVP on 01/11/17
After party info and dietary requirements have been included in e-mails
JH to send invites to DCMS panel and filter into seating plan
JH to chase Jacqui Gay for names of 10 x invites 
RC to distribute SLT invites
JH to add guest list into Sharepoint (locked)

  - Guest Accreditation / Wristbands
Wristband to say “Turner Prize 2017 Award Ceremony”
Black deboss with gold infill / Black deboss with no infill

- PRESS

- JH/BM to clarify Bolton & Quinn invite list – send PDF invite to targeted critics and correspondents

- LM to arrange with space in Ferens for Front Row - 28/29 November

- 4 x artists to be briefed on 05/12/2017 prior to the announcement. Brief to be sent in advance as well as briefed on the day
BM to arrange B&Q to do this / LM to contact artists about schedule

- Press file from 15:00 – 19:30 in Live Art Studio – who are the privileged few who know the winner? BM to confirm

- Location TBC for briefing media - likely to be Ferens
BM to confirm time and who is briefing them

- KF agreed pitching Martin Green and Cosey Fanni Tutti to BBC for interviews - awaiting RSVPs - BM to liaise with B&Q for other Art world interviewees

- MB confirmed press are filing in Trinity Square café from 18:00 for no cost (cover costs of coffee) MB to test Wi-Fi

- Goldie – any expectation from Press? BM to clarify

- PRODUCTION

- Overview schedule is now in Sharepoint – all to feed into it

- JH to chase Eimear and John about BBC production details – trucks for road closures – JH also to request this from Saunts

- CC to chase up Durham / HPSS

- JH to send centrepiece brief to JZ Flowers – LM to share contact

- LM/JH to discuss name places and seating plan design – list table number next to guest names on guest list

- LM to speak to Laura Smith about the name places to tie in with the invite design

- JH to look at areas in Minster for volunteer break out area / Cry room for artists / storing kit for 28 x crew

- CATERING

JH to meet Saunts and go through menu
JH to confirm wine order with Saunts once menu is confirmed

- AFTER PARTY
Steve Cobby to DJ after party in addition to Minster
2 x DJ spec booked out from HPSS for both locations
RC to complete a TEN for HSG – 11:00 – 02:00
JH to confirm and book SIA for Ferens / Minster / HSG

- BUDGET
JH/CC/LM to meet to go over budget on 02/11/2017

- CONTRACTS 
Steve Cobby
Goldie
Durham Marenghi
Portaloos
JZ Flowers

Minster, venue agreement needed?
Tate / BBC

Framework Agreement addendums:
Saunts
HPSS
First Aid
Security
Traffic Management (tbc)

- AOB
LM to arrange 2 x BBC Academy as runners at Ferens
RC to inform Lorrie that Steve Cobby will be DJ’ing Ceremony

JH/LM to get costs for Turner Prize T-Shirts for Minster volunteers, staff and crew