## Sheet1
Audience Development Plan - Depart
Objective | Activity | Resources | Monitoring and measuring results | Date
To achieve and exceed audience targets | Produce overarching marketing packs and bespoke support to venues using audience insight data | Promoter selling collateral | Audience numbers | From project launch to end of tour
| Deliver social media/online campaign for venue touring | Marketing collateral/develop local relationships, identify networks and gatekeepers | LIFT, Circa and local partner analysis & evaluation - inform plan for follow on activity with audiences | From project launch to end of tour
| Deliver joint, but centrally managed, PR campaign for depart tour | Work with PR expertise (including online PR experts nationally and locally) to create strong, sustained, shareable PR content. Identify key bloggers and online voices in outdoor performance as well as artforms / interest areas featured in Depart (eg choir, music, dance) | Analytics of online reach & engagement from on-sale date, through campaign and post event | From project launch to end of tour
| Work collaboratively with partners to create/deliver marketing campaigns for the tour, achieve economies of scale, and share local knowledge | Develop strong brand for depart, engaging content targeted to specific audiences, imagery, film and video contentl, behind-the-scenes content and DM/E-marketing collateral | Use Spektrix ticketing reporting to evaluate promotional campaign, ROI, and monitor against PR coverage - measuring effectiveness of messaging, timing, tonality, to inform ongoing and future plans | From project launch to end of tour
|  | Develop content for marketing and online / digital collateral | Evaluate audiences at each venue / festival performance of depart numbers, demographics, behavioural and attitudinal data and inform future plans (questionnaires, vox pops, online survey monkey etc) | From project launch to end of tour
|  |  | Monitor outreach / participatory activity qualitatively | From project launch to end of tour
|  |  | Collate and report all partner evaluation, audience numbers and data, online analytics, PR coverage and build strategic development plan for future audience growth | From end of tour
To increase the range and diversity of audience members and participants for outdoor performance and circus | Use the tour to pursue new opportunities to present outdoor work and promote to diverse and disengaged audiences through the strategic use of partnerships in areas of low engagement (cold spots) and share audience data and knowledge build long-term audience development both in the 2017 tour locations and other idfentified areas of need. | Develop networks, partnerships & relationships/data feedback tools (cards, online surveys, social media sharing tools) | Evaluate reach of tour audience makeup against key target segments and monitor similarities / differences in each location. Evaluate reach in areas of low engagement, and use findings to inform future programming and marketing activity. and develop bespoke ongoing CRM strategy with core target segments | From end of tour
| Maximise opportunities that arise from current and future partnership with Circa and regional presenting partners to attract wider audience base for outdoor performance | Develop relationships, agree ongoing audience develop objectives and agree 3 - 5 year delivery plans | Monitor bookings, tour variations, reactions to campaign activity, audience feedback/data collection and build database for e-marketing and audience CRM strategy | From end of tour
| Conduct feedback surveys, vox pops and online surveys at each venue, participate in Audience Finder postcode analysis & actively encourage completion of standardised e-mail survey. Standardise at all tour locations and collate data | Develop feedback tools (online and off) record postcodes/ Email addresses,ticket buying reports & e-surveys | Analyse audience feedback/ response rates/Audience Finder report – create action-focused report to share amongst partners and more widely within sector. Use to inform future plans and other large scale outdoor / circus events | From launch to end of tour
To work with venues/producing and presenting partners /project leaders to learn more about our audience/participants | Develop contractual clauses &/or data sharing agreements with all tour venues and partners | Develop relationships, reports to be shared | Evaluate Audience Finder data response after each stage of the tour and agree strategies to increase response | From project launch to end of tour
| Participate in Audience Finder - ‘Touring’ & ‘Outdoor Arts’ clusters & submit postcodes data post-tour | Audience Finder reports | Evaluate return, responses and the usefulness/quality of data | From project launch to end of tour
To use the knowledge gained through the 2017 tour to retain and build audiences for outdoor performance and circus by creating a 3 – 5 year audience devlopment plan | Meet face-to-face with alll venue partners to agree marketing and audience development objectives and activity plans, follow up with meeting or Skype/Google Hangout /conference calls to cement relationships, encourage data sharing & increase knowledge about audiences and effectiveness of activity. | Feedback cards, online surveys, social media /e- mail addresses & e-surveys. Marketing collateral/develop relationships. Set clear objectives and monito | Evaluate reports, share across depart tour venues, analyse and agree future strategy at end of tour planning meeting | From end of tour
| Exit flyer at all performances with feedback cards | Marketing collateral | Use evaluation and data from all partner evaluation re: targets, audiences & numbers and campaign activity findings to inform future outdoor large scale plans and CRM strategy for new audiences | From project launch to end of tour
| Agree commitment from all venues, project partners & festivals to participate in Audience Finder, understand the benefits of data sharing, and create joint plans | Set reporting specifications to meet audience development objectives | Evaluate all audience feedback and Spektrix ticketing / buying reports – share findings | From project launch to end of tour
| Follow up audience feedback – submit postcodes for Audience Finder e-marketing survey across venues | Develop 3 - 5 year plan with all four partners agreeing joint and independent local activity for audience development and committed plan to share, analyse, and make decisions based on data |  | From end of tour
| Obtain, use & share results of Audience Finder reports with contacts/networks - inform plans & strategies |  |  | From end of tour
| Develop close working relationships with venue partners to gain solid understanding of audiences, what works best, increase audience intelligence and increase numbers and diversity of audiences |  |  | From project launch to end of tour
| Work with the four partner venues on pilot marketing initiatives to develop their audiences and feed into a national pitcure for developing outdoor performance audiences | Agree pilot activity, marketing collateral (online and off) |  | From end of tour
| Share audience findings from each depart show as the tour progresses with subsequent venues to inform marketing plans |  |  | From end of tour
To offer participation opportunities and contextual events to run alongside the performances and create opportunities for deeper and enhanced engagement possiblilities | Identify key local schools and community, dance and choir groups in each of the four areas, build joint objectives with them, gain understanding of their needs, activities, ways of engaging their own students / community members and produce bespoke plan for each to work with them over a sustained period leading up to 2017 and in the three year period following. | Develop relationships & specific collateral / tonality for each | Share findings with education and community and artform groups, share knowledge of what marketing worked, audience insights, and build wider network. Evaluate use and effectiveness of any resource packs / materials created through qualitative feedback session with leaders. | From project launch to end of tour
| With our dance, circus and choir partners (list partners) in each region, deliver participation opprtunities and workshops across a wide range of contextual activity, including professional development for artists, CYP and members of the public. Use networks to market the programme and build into a programme of ongoing activity post-tour. | Participatory / contextual programme. Marketing collateral and plan | Evaluate response to events and promotion. Conduct participant evaluation, documentation via film, images & comments - research rolled out across tour venues and to develop blueprint for wider use nationally, using findings to inform future development plans and initiatives | From project launch to end of tour
| Work with teachers, community and activity group leaders to agree and deliver this | Relationship building. Set objectives. Delivery plans. Monitor. Follow up in group performance deals | Evaluation criteria for success (these may differ for each community group depending on objectives) | From project launch to end of tour
| Offer access to performers and company members so that audience members build a closer relationship and deeper knowledge of 'behind the scenes' and a sense of ownership of the show. Both real time and digitally | Agree programme. Build tools | Measure engagement through surveys and online / social media feedback | From project launch to end of tour
To maximise the number of people engaging with, and accessing, the tour online | Create a web platform for the tour that is 'mobile first' allowing people to access information about the show, engage and comment, post images, video and pictures principally via phones and tablets | Build web strategy, develop platform, monitor | Web analytics | From project launch
| Use the most effective social networks and tools that will reach and engage our target audience and create content that they will want to share | Create content and measure sharing. | Measure sharing | From project launch
| Build a robust and increasing online database of our audience, and to be able to segment this in the most effective ways for future marketing and CRM | segmentation tools via Spektrix, embedded into website | web analytics, Spektrix reporting | From project launch to end of tour
| Create a digital marketing strategy that will build noise and engagement throughout the lead up to the show, during the tour, and post-tour. | Agreed Strategy | Ongoing evaluation and refining | From project launch
| Monitor, update & amend strategies following regular monthly analysis of online/social media audiences and responses to campaign | Ongoing analytics and measuring | Ongoing analysis, interpretaion and refining | From project launch to end of tour
| Use data collected at the end of the tour to understand connection between our audience’s online pattern & behaviour with that of the live performances | analysis via Spektricx and analytics. Potential to use external agency to help |  | From end of tour
| Develop loyal/long term audiences by increasing engagement & frequency of online interaction across social media platforms and Spektrix ticketing functionality | Reporting. Develop in to CRM Strategy | Ongoing analysis | From project launch to end of tour
| Offer 360 degree access to the artists online - share behind the scenes coverage, interviews, films of creative process and live performance | Content and distribution |  | From project launch to end of tour
| Ensure accessibility of depart - embedding, integrating & cross posting & providing access to contextual performances and material | Content and distribution |  | From project launch to end of tour
| Audit social media platforms at end of tour to respond to online trends & develop new platforms accordingly | Joint evaluation and action meeting |  | From end of tour
| Use depart to research possibilities for incorporating new technology - including researching technology such as augmented reality for future tours / outdoor performance events | Evaluate new technology - relevance and cost effectiveness for target audience. Create content |  | From project launch to end of tour
| Ensure data capture call- to-actions are on all relevant web pages | Web developer brief |  | From project launch to end of tour
| Measure the success / effectiveness of tour e- marketing campaigns | Analytics weekly / monthly. Tag campaigns |  | From project launch to end of tour
| Encourage ‘online takeovers’, Twitter Q&A’s etc. from artists, dance and choir members throughout lead up to tour | Briefs for participants, online analytics | Monitor interaction rates | From project launch to end of tour
| Investigate involvement, utilise findings/networking & marketing opportunities from AMA CultureHive | Test out blogs and relationships | Assess impact | From end of tour
| Develop online/social media competitions/offerings in relation to new touring shows | Online collateral. Distribution | Measure response. | From project launch to end of tour
| Use strategic online advertising (facebook advertising) in line with digital strategy, to reach and engage specific audience / interest groups | Collateral / engaging content for target audience | Measure response | From project launch to end of tour