## Sheet1
Yorkshire Festival : Place Des Anges by Gratte Ciel - Draft Timeline 2016
2016 | w/c | Creative | Administrative | Community | Marcomms, M&E | Lead | Notes | Key Impacts
February | 1
8
15
22
29
March | 7
14
| 21 | Meet with Partnerships (24 March). Artists & York Fest contracts signed? PID done? |  |  |  | KF | Hospitality arrangements/expectations discussed. | EASTER
| 28 | Partnerships sending out Save the Date to partners |  |  |  | LR | Chris/Mel talking to College about using College for reception | EASTER - Katy Off
April | 4 | TG contract signed? Road closures agreed? All permissions in place? |  |  |  | KF | Access to buildings (eg. external stairway to police stn roof). Structural Engineer. | EASTER
|  | Meet with police, council, college re. Permissions (date tbc but prior to 14 April) |  |  |  | KF | HW to set up meeting
|  | Meet with Rick of AJF (5 April?) |  |  |  | HW | LR feedback news to marketing
| 11 | Yorkshire Festival Launch (14 April) - TG Events provide draft EMP |  |  |  | KF | EMP checks: Crowdcontrol, Evac, Med, safeguard, MS/RA issues
|  | Meet with Marketing & David re. detailed plan & meet with Elinor re. M&E |  |  |  | LR | Press arrangements discussed. Elinor: Volunteers for surveys or online?
|  | Ticket issues to be discussed with David. Accreditation system/access? Partners, etc tickets issued? |  |  |  | KF | Arrangements for tix if not sold out (box office?) or if sold out (waiting list?) Security counting at gate/s?
| 18 | Artist's hotel rooms booked? Taxis required to/from airport and/or hotel/site? Catering sorted? |  |  |  | HW
|  | Issue EMP to authorities (for sign off on 12 May). Traffic Order in place? |  |  |  | KF
|  | Earlier event elements? (Note AJF activity?) Catering/commercialisation? Local restaurant offers, etc? Draft FAQs? Branding arrangements on site - including Hull 2017 tent? |  |  |  | LR | FAQs: Parking, accom, access, food, other ent, best viewing spots, lost items/kids, feather facts, etc? Meet with Patrick/Phil re. Branding/commercialisation.
| 25 | Feedback from authorities (for sign off on 12 April) and updated EMP issued? |  |  |  | KF
May | 2 | Role of volunteers on site agreed? Monitoring role? Who responsible/briefing them? |  |  |  |  | Monitoring role discussed with Elinor (LR)
| 9 | ESAG (12 May) to sign off EMP. Letter drop to local residents? |  |  |  | KF | Letter: why, days of noise, road closures, tel no? - and come to event! Tix enclosed or available from...?
| 16 | Tickets available approx 6 wks prior to show (date to be agreed). |  |  |  | LR | General distro of event specific print? FAQ online.
23
30
June | 6 | ESAG (9 June)
| 13 | Post-event marketing in place? Photographer/film arranged/briefed? |  |  |  |  | Photographer/film costs from marketing
20
Show Week | 27 | Production meeting (June 27) Arrival of Grattte Ciel, set-up, rehearsal, *SHOW DAY* (2 JULY) & get out/site clearance |  |  |  |  | See more detailed schedules | YORKSHIRE FESTIVAL / AMY JOHNSON FESTIVAL
July | 4 | Gratte Ciel depart (4 July). Site clear? Pay artists & contractors. FEU? Post-event marketing. Update Hull2017 website?
| 11 | ESAG Meeting (14 July) Debrief. Evaluation/updates to partners?
18
25