## PID
Project name | COUM Exhibition and performances
Last updated | 2016-02-05 | [5 empty] | Objectives & metrics
[7 empty] | Metrics |  | Target |  | Forecast/actual
Related documents | [6 empty] | # audience |  | 20600
Project plan | Draft |  | Risk management plan |  |  | Pending |  | Hull residents |  | Y
Budget | Draft |  | Marketing & comms plan |  |  | Pending |  | regional |  | Y
[8 empty] | national |  | Y
Dates | [7 empty] | international |  | Y
Project start date | 2016-02-29 |  | Project live date |  | 2017-01-01 |  |  | children (<16) |  | N
End of Live date | 2017-03-31 |  | End of eval. date |  | 2017-04-30 |  |  | young people (16-25) |  | Y
[8 empty] | families |  | N
Categories | [7 empty] | older people (60+) |  | Y
Type | Hull 2017 Production |  |  | Strand |  | Humber St Arts Programme |  | self-identify as disabled |  | Y
Season | Made in Hull |  |  | Digital requirements |  | High |  | BME |  | Y
[8 empty] | NEET |  | N
Finance | [6 empty] | # temporary jobs created |  | tbc
Total project budget |  | 101000 |  |  |  |  | # freelance contracts created |  | 4
Hull 2017 contribution |  | 101000 |  |  |  |  | # participation opportunities
Analysis/project code(s) |  | tbc |  |  |  |  | of which for school age
[7 empty] | # commissions |  | 4
[7 empty] | Objective |  | Met? | Notes
Show Hull as home to groundbreaking, globally significant artistic movements
People | [6 empty] | Generate international interest in Hull 2017
Project Lead | Sam Hunt |  |  | Volunteering lead |  | Shaun Crummey
Producer | TBC |  |  | Education lead |  | Ian Read | Create new audiences for contemporary visual art and stage a critically well received exhibition for existing ones.
Assistant Producer | TBC |  |  | Marketing lead |  | Laura Smith
Production Manager | TBC |  |  | Community Eng lead |  | James McGuire | Drive footfall to Humber St
|  |  |  | Evaluation lead |  | Elinor Unwin
Performance, Residency & Legacy
What is the model for delivering this project? eg we will employ a creative team, we will outsource to an agency, we are contributing funding but no other resource… | [6 empty] | Performance: Summary of events, including dates, times, venues, ticketing strategy (free/paid, (un)ticketed), age guidelines (free text OR UKFC categories) etc. NB Do not duplicate information stored in Artifax.
Hull 2017 will be responsible for the overall programme and management of the space at 64 Humber St. There will be a curatorial and gallery management team in place to facilitate and support the creative teams and artists engaged to deliver specific exhibitions, performances and events. Invariably this will mean the lead producer working directly with the creative team responsible for the particular programme, overseeing the install and opening then handing over day to day management of the space to the venue management. | [6 empty] | This is in effect a small festival, designed to highlight the importance of COUM within the context UK art history, the development of live and sonic art and their vital role in the emerging counter cultures of late 1960s and early 1970s. There is a spirit of artist, personified by both Cosi Fanni Tutti and Genesis P-Orddige and this is an opportunity to explore where that ‘type’ of artist can be found in contemporary practice. As much as it is about the work of COUM and their continuing influence, it is about the city that COUM was founded in, a place that gave space to artists to experiment and was instrumental in the development of both artist, this is a story not widely known and something Hull can rightly take ownership of, one that speaks to the defiance, rebellion and local innovation that this city defines itself by. The main body of the programme will be an exhibition featuring exhibits from the archives of Cosey Fanni Tutti and Genesis P-Orrdige. This will endeavour to tell the story of COUM up to the seminal ‘Prostitution’ show in 1976. Alongside this will be a programme of live events, talks, music, club nights and new commissions which will celebrate the artists who best typify the spirit of COUM now. with a clear focus on opening and closing events.
How will delivery partners be identified and procured? Refer to the procurement flowchart and note below the agreed process (A–G) for each contract. | [6 empty] | Residency: How will you realise your residency work? What opportunities will be created within the project for our education programme? How will the project help to build new audiences through engagement? Note numbers, types and duration of participation opportunities.
Both Cabinet Gallery (curator exhibition) and The Quietus (curator live events) were identified as delivery partners through the lead artist Coesy fanni Tutti and as such are artistic decisions sitting outside of procurement regulations. Serious, who may provide additional support to teh live events, were identifued through an open tender process to engage a music production partner. | [6 empty] | There will be limited opportunities for residencies although there will be a commitment from lead artist Cosey Fanni Tutti to appear throughout the run of the exhibition for performances, talks and symposia.
Who are the delivery partners? (Contact & organisation name, contract status for each) | [6 empty] | Legacy: What is built into the core project that will ensure legacy?
All partners are currently in place but awaiting contract, the project is led by Hull 2017 with creative input from Andrew Wheatley (Director Cabinet Gallery) and responsible for the relationship with lead artist Cosey Fanni Tutti who between them have curatorial and creative control of the exhibition and associated programme of talks and any publications. The live events element of the programme is being led by online culture magazine The Quietus, led by editor Luke Turner and reviews editor Sophie Coletta with additional support from John Cummings at Serious. Andrew Wheatkey - art@cabinetltd.demon.co.uk : Luke Turner - luke@thequietus.com : John Cumming - john.cumming@serious.org.uk | [6 empty] | The project will help re-position Hull in terms of the city’s role in shaping late 20th century counter culture, framing the city as place of inspiration and experimentation, a place where artists have made globally significant work which may be at odds with the accepted view of the city.
Volunteer management: What is your expectation of volunteer requirements? (Numbers, roles, responsibilities, duration / period required) | [6 empty] | Project description (200–400 words) for use in marketing materials, on webpages etc. Note that this may be edited.
The opportunities for volunteers will be identified through the operational plan for the managemnt of the gallery space at 64 Humber St | [6 empty] | The opening season of Hull 2017 is ‘Made in Hull’ and is an opportunity to re-visit and re-tell the key stories of the city in new and interesting ways. It is also the opportunity to begin to tell stories of Hull that may not be so well known to its residents or the wider public, stories that will help reposition the city in terms of its contribution to culture, stories like the formation of COUM Transmissions and it’s evolution into Throbbing Gristle, the genre defying live art, noise terrorists that helped define 1970’s counter-culture and especially to two lead creative forces in both these groups, Genesis P-Orridge and Cosey Fanni Tutti and their relationship to Hull. This will be the opening exhibition for 64 Humber Street, the new contemporary visual arts space for the city. The venue will be owned, ran and curated by Hull 2017 it will be a space that helps develop audiences for contemporary visual arts in the city in anticipation of the Turner Prize and it will also host significant exhibitions in their own right. This opening exhibition is designed as a statement of intent, it will uncover a story the city has not yet told. The exhibition is the celebration and exploration of the living legacy of COUM and in particular the artist Cosey Fanni Tutti and Genesis P-Orridge. Although the main body of the exhibition will be made from artefacts it will not be a museum show, the continuing legacy of COUM will be represented through an associated live programme featuring artists who best embody the spirit of COUM, there will be talks, in conversation style events and the publication of an occupying catalogue featuring series of new commissions exploring the contemporary legacy of COUM.
Version control
Date | Changes and/or approvals
2016-02-05 | To CEO for greenlight
ACE
British Council
HLF
Treasury
University of Hull
Big Lottery
Health
Spirit of 2012
Trusts & Foundations
Key funders

## Option sets
Status | Type | Strand | Season | Digital | Y/N
Completed | Hull 2017 Production | 365 Grant Fund | Made in Hull | Very high | Y
Draft | Hull 2017 Commission | Blast Theory | Roots & Routes | High | N
Pending | Co-commission | Caravan of Love | Freedom | Medium
| Funded (strategic partner) | Circus | Tell the World | Low
| Funded (presenting) | Codhead | Curtain Raisers
| Grant-funded | Curtain Raiser 2016 | Thru 2017
| Non-funded (strategic partner) | Dance | Post-2017
| Non-funded (presenting) | Digital commission | n/a
| Non-artistic | Film
Freedom Festival
Fuerza Bruta
Hull 2017 @ New Theatre
Hull Truck
Humber St Arts Programme
Land of Green Ginger
Literature commission
Look Up
Museums / Libraries service
Music
Neighbourhood Network
New Years Eve
PRS New Music Biennial
Radio 1 Big Weekend
Singing City
Site-specific theatre
Slung Low
Street animation
Theatre Sector dev & commissions
Turner Prize