And Now:

Site Prep

Mandy will keep Adam posted about dimensions in terms of turf over turf, or removing turf for bonfire site. This would need to happen before And Now: arrive – Adam agreed this can happen.

Adam will check the ground for any services before arrival for putlocks .

Delivery

Difficult through estate.

7.5 tonne delivery on morning of Monday 10 July. Adam will get postcode for delivery. There will be a telehandler onsite. Adam will drive telehandler.

Arrival

Sunday 9 July.

Pyro in van loaded into container. Might be able to use one of Eastmount’s – Adam will sort container either way.

Container also to be used for working in. 20’

Security

Hull 2017 will provide. Security onsite from Sunday 9 July and enhanced for show day.

Build

Heras fenced round build compound.

Mandy will confirm footprint.

Heras will be removed for show – rope and post used if needed.

Heras provided by Hull 2017.

Welfare

Hull 2017 to sort. *MM will discuss with Lone Twin in terms of their plans and ensure a space is available in Eastmount for welfare.

Toilets

Some up by bonfire. Hull 2017 will provide.

Radios

Hull 2017 will provide.

Staffing

Stewards back of house.

Hull 2017 Volunteers front of house – potentially behind rope.

Risk Assessment

And Now: may supply some low level pyro.

GH happy with risk assessments being done dynamically in the week of the event. Good relationships with fire department.

PA and Power

Hull 2017 will provide.

Radio mics and engineer also possibly needed for compere?

Timings

21:23 sunset

21:23-22:00 preamble

22:00 fire lit

22:20 probably finish

Weather

As bonfire is round, the audience could be moved if wind is blowing in their direction.

Parking

Hull 2017 to look at options outside of estate.

Bonfire Contents

Burn 60x60x60cm crate at top of bonfire.

Wood ordered.

Bottom of fire could be packed with packing crates. Adam will bring to site.

Tea

Samovar to make tea.

And Now: would like to make tea and hand out to people as they’re gathering. Copper water boiler.

Heated by charcoal – front line of audience. Guild would be giving out the tea.

All streets are names of rivers, so water could be collected from each river.

Something like 500 cups.

Site dressing

Flagpoles and bunting – And Now:

Adam will look at providing poles.

Music

Mandy thinking that Lone Twin choral thing up to point and then And Now:’s music would take over with pre-recorded music – 3 tracks. Fun.

Lighting

Hull 2017 could provide, but will discuss with Lone Twin.