## Production costs
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | Notes 30/06 | Telephone | email | Order wording | Order cost exVAT | Insurance values
LIGHTING |  |  |  |  | They bring
Lighting stands | L.A.D. events/3d | 140 |  |  | 4 x 60Kg stands with T-bars | 2m height need 6 now! | got verbal quote from Josh 26/06, asked 3d for quote | [5 empty] | 500
Lighting stands | 3d | 228.4 |  |  | 4 x 60Kg stands with T-bars |  | invoice received | [5 empty] | 800
site lighting | TGPS | 250 |  |  | Festoon etc | [7 empty] | 750
LIGHTING SUB-TOTAL |  |  |  | 618.4
AUDIO |  |  |  |  | They bring all but PA
FOH Pa | 3d productions | 7238.2 |  |  | 4 x hangs of V series | max 350Kg per hang | invoice received | [5 empty] | 120000
Install crew | 3d productions | inc above |  |  | 2 crew in & out | £200 per day | invoice received | [5 empty] | inc above
PA tech | 3d productions | inc in C11 |  |  | 3 days at £220 per day |  | invoice received | [5 empty] | inc above
crew transport | 3d productions | inc in C11 |  |  |  |  | invoice received | [5 empty] | inc above
Delivery | 3d productions | inc in C11 |  |  |  |  | invoice received | [5 empty] | inc above
Accomodation and subs | 3d productions | inc in C11 |  |  |  |  | invoice received | [5 empty] | inc above
additional speaker stands | 3d productions | 64 |  |  |  |  | invoice received
additional deck | 3d productions | 28.8 |  |  |  |  | invoice received
multi | 3d productions | 24 |  |  |  |  | invoice received
AUDIO SUB-TOTAL |  |  |  | 7355
STRUCTURES
dressing room tent | Nationwide | 607 |  |  | 6m x 9m | with floor & lights | invoice received 15/08 | [5 empty] | 5800
booth tents | Nationwide | 330 |  |  | 3 no. 3m gazebos | staked | invoice received 15/08 | [5 empty] | 1500
Lost kids gazebo | TGPS | 50 |  |  |  |  | invoice received | [5 empty] | 350
furniture | Nationwide | 29.5 |  |  | 4 x trestles,10 x chairs |  | invoice received 15/08 | [5 empty] | 480
delivery | Nationwide | 250 |  |  |  |  | invoice received 15/08 | [5 empty] | ---------
additional chairs | city furniture hire | 142.8 |  |  |  |  | paid on credit card
STRUCTURES SUB-TOTAL |  |  |  | 1409.3
POWER & DISTRO
Show power | John F Hunt | 920 |  |  | 2 x 150KVA | Sync'd to load share | invoice received | [5 empty] | 56000
tank | John F Hunt | 24 |  |  | 1 x 1000l tank |  | invoice received | [5 empty] | 1500
production power | John F Hunt | 150 |  |  | 20KVA |  | invoice received | [5 empty] | 9950
tank | John F Hunt | 24 |  |  | 1000l tank |  | invoice received | [5 empty] | 1500
site sets | John F Hunt | 300 |  |  | 2 x 20KVA | for festoon etc | invoice received | [5 empty] | 9950
Fuel | John F Hunt | 900 |  |  |  |  | invoice received | final figures received 17/08 |  |  |  |  | 2000
Delivery | John F Hunt | 1120 |  |  | delivered Monday, collected Tuesday |  | invoice received | [5 empty] | ----------
.
Distro | IDE | 304 |  |  | as required |  | invoice received | [5 empty] | 2200
cable ramp | IDE | 300 |  |  | 50m |  | invoice received | [5 empty] | 7500
delivery | IDE | 130 |  |  |  |  | invoice received | [5 empty] | ----------
tower lights | John F Hunt | 576 |  |  | 4 x LED |  | invoice received | [5 empty] | 42000
POWER & DISTRO SUB-TOTAL |  |  |  | 4748
PLANT & BARRIERS
ped barrier | Live | 1375 |  |  | 150 ped barriers |  | ordered 27/07 | [5 empty] | 6200
Heras | Live | inc above |  |  | 40 x heras sets |  | ordered 27/07 | [5 empty] | 1600
extra heras | Live | inc above |  |  | 80 x heras sets | for match | ordered 27/07 | [5 empty] | 3200
delivery | Live | inc above |  |  | 2 loads £50 e/w pl | delivered 7th, collected on 15th | ordered 27/07 | [5 empty] | -------
forks | Nixons | 540 |  |  | 3.5t all terrain forks |  | invoice received | [5 empty] | 32000
telehandler | Nixons | 205 |  |  | 7m telehandler |  | invoice received | [5 empty] | 38000
Fork extensions | Nixons | 17 |  |  |  |  | invoice received | [5 empty] | 1000
fuel | Nixons | 70 |  |  |  |  | invoice received | [5 empty] | 100
delivery | Nixons | 340 |  |  | delivered Mon 7th, collected Tues 15th |  | invoice received | [5 empty] | --------
crane | Central crane hire | 900 |  |  | 30t crane for 2 days | £450 per day | ordered 22/07 | [5 empty] | ----------
Trakway | Live | 2491.2 |  |  | as plan |  | ordered 27/07 | [5 empty] | 91000
Trakmats | Live | 1650 |  |  | 50 x trakmats |  | ordered 27/07
PLANT SUB-TOTAL |  |  |  | 7588.2
CREW
Site crew | Tge | 600 |  |  | 1 man Tues, Weds, Sat | Rich Moore | invoice received | [5 empty] | --------
additional crew | TMC | 927 |  |  | 6 men, Saturday, 0900-1300 & 1700-1900 | for additional fencing | invoice received | [5 empty] | ----------
stage hands | TMC | 3090 |  |  | 16 x 10 hr days & 6 x 5hr get-out | £15 per hour | invoice received | [5 empty] | ----------
lighting techs | TGE | 1800 |  |  | 7 man days @ £200 plus 2 for get-out @ £200 | £200 per man | invoice received | [5 empty] | -----------
PDs |  | 125 |  |  | 7 days @ £25 | For lighting techs | invoice received | [5 empty] | ----------
mileage |  | 100 |  |  | charged @ £0,40 per mile | For lighting techs | invoice received | [5 empty] | ----------
CREW SUB-TOTAL |  |  |  | 6642
MISCELLANEOUS
comms | 900 comms | 409.43 |  |  | 36 x DP3400's |  | ordered 24/07 | [5 empty] | 14400
CAT scanner | HSS | 280 |  |  | to scan ground before we stake |  | paid on TG CC | [5 empty] | 450
Cleansing | Hull CC | 874.01 |  |  | clean on Sunday 13th & Tuesday 15th |  | invoice received | [5 empty] | ---------
Bins | Hull CC | 274 |  |  | 2 x 1100l & 8 x 240l bins | delivered Tues | invoice received | [5 empty] | 2500
backstage toilets | add plant | 200 |  |  | 4 x single plastics |  | ordered 22/07 | [5 empty] | 2400
service | add plant | 240 |  |  | 2 x service |  | ordered 22/07 | [5 empty] | -------
Audience toilets | add plant | 860 |  |  | 14 x single plastics and 2 x wheelchair accessible units |  | ordered 22/07 | [5 empty] | 10800
servicing | add plant | 250 |  |  | 1 x service |  | ordered 22/07 | [5 empty] | -------
del/coll | add plant | 120 |  |  |  |  | ordered 22/07 | [5 empty] | ---------
consumables | ??? | 100 |  |  | tape, cable ties etc | [7 empty] | 100
MISCELLANEOUS SUB-TOTAL |  |  |  | 3607.44
STEWARDING
stewarding and security | Prestige | 7222 |  |  | stewarding, as spreadsheet | inc lost kids | ordered 22/07 | [5 empty] | -------
Car park stewarding | KCOM | 1102.35 |  |  | stewarding, as required, for carpark management |  | ordered 04/08 | [5 empty] | --------
additional stewarding | Prestige | 200 |  |  | additional 4 SIA for Sunday night |  | ordered 13/08
STEWARDING SUB-TOTAL |  |  |  | 8524.35
H&S
Fire extinguishers | TGE | 100 | [10 empty] | 500
Show first aid | Heart Medical | 1464 |  |  | for both shows |  | ordered 22/07 | [5 empty] | ----------
additional medical | Heart Medical | inc above |  |  | for Sunday night |  | ordered 12/08
H&S SUB-TOTAL |  |  |  | 1564
TM
TM | centurion | 375 |  |  | Event parking signs |  | received quote 08/08 | [5 empty] | 1200
TM SUB-TOTAL |  |  |  | 375
FEES
Handling fee | TGPS | 2121.5845 | [10 empty] | --------
FEES SUB-TOTAL |  |  |  | 2121.5845
TOTALS Ex Contingency, Ex VAT |  | 44553.2745
Contingency |  | 7046.7255 |  |  | 5% contingency
TOTALS inc Contingency - EX VAT |  | 51600
TOTAL inc VAT |  | 61920

## TGE Fees
Item | Cost ex vat | Description | Notes
Production Prep time | 1250 | 5 Days @ £250 per day
H&S prep time | 1250 | 5 Days @ £250 per day | Not including meetings
Site/production manager | 3150 | 9 Days @ £350 per day | Monday - Tuesday
on site H&S | 0 | 2 Days @ £420 per day | Gareth to do
Meetings | 500 | 2 meetings @ £250 | ESAG plus one other
mileage | 240 | 4 Round trips of 150 miles @ £0.40 per mile
accomodation | TBP | ? Rooms for ? Nights
PD's | 275 | charged at £25pppd | 11 man days
TGE TOTAL Ex VAT | 6665
In addition, Hull 2017 will provide and pay for:
Hotel accommodation for Site / Production Manager and Safety Manager as required over the build / event period