## Sheet1
Task | Owner | FEB | MARCH | APRIL | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MARCH | APRIL | MAY
Cabinet Contracted | CoC
Quietus Contracted | CoC
Archiving Cosey | CG
Archiving Tate | CG
Writers commissioned | CG
Live artists contracted | TQ
Content Finalised | CG/TQ/CoC
Designs confirmed | CG/CoC
Press Launch | CG/TQ/CoC
On Sale (tbc) | CoC
Exhibition plans submitted | CG
Publication Finalised | CG/TQ/CoC
Install | CG/CoC
Exhibition | CoC
Live Events | CG/TQ/CoC
Evaluation | CoC