HCAL/Hull 2017 Troubleshooting Meeting

Attending:

Hull 2017 - Sara, Katy, Lily, James, Phil

HCAL – Simon, Peter, Kirsten, Maxine, Esther, David, Jane

To Do

| Item | Lead | Notes |
| --- | --- | --- |
| Write one pager on stakeholder events | Katy | Send to Simon/Peter/Jane |
| Send read access to Ferens Outlook calendar to Hull 2017 | Jane |  |
| HCAL confirm BMS closure Dates | Simon/Peter | Should know by CoP today. Suggested closure is 5th-11th inclusive. |
| Clarification on Big Draw | Jane | ASAP if it needs to go in to print |
| Roles and responsibilities list for sign off/enquiries | Lily/HCAL |  |
| Dates for volunteer training to Jane | Lily |  |
| Supply FoH list to join for Turner Prize volunteer training | Haley |  |
| Set up meetings (all ASAP) | Lily | - Venue Operations meeting - Explore Art meeting - Simon and Katy meeting |
| Supply Explore Arts costs for technical deinstall | Jane and Esther |  |
| Send major deadline list to Simon | Sara |  |

Project Management

- Project management strategy - Very clear working groups, nominated person from each group, hierarchical feed up to higher levels if needed

- 2 troubleshooting/issues meetings between now and the opening with everyone at key sign off points – what are these?*

- HCC to deal with Ferens marketing and comms from their side. Any artwork approvals to come from Anna at HCC.

- Jane to come to venue operations meeting* to manage the day to day Ferens diary

Build and Operations

- Closure 5th - 11th inclusive, but we can be in working alongside BMS team in the spaces.

- If there is an issue, we agree as a team to cover the resources

- Budget saving from Turner Prize Supervisor jobs can be put in to another part of the Turner Prize budget, everyone agreed. Plan is to go with 4 staff members for now. No clarification on holiday pay.

- Operational detail of the jobs – not to give tours, security of the work as a main focus

Learning Programme

- No management fee to Heritage Learning. Turner Prize removes the risk and supports income generation to Heritage Learning.

- Jane and her team to work with Hull 2017 for Saturday workshops. Comms should be clear that the price has been subsidised to make it accessible.

- Need more input from Heritage Learning about Big Draw and how we can support. ASAP if it needs to go in to print.

- Jane has sent through David’s costs for the Big Draw and Future Ferens involvement*

Explore Art

- Jane on board with the idea, v excited about having ‘hub’ space in the middle. Brilliant idea, fantastic to have a space that reflects all the audiences

- We have to have a targeted under 5’s space – NPO delivery plan, 3m of funding – conference on 12th

- Jane and Esther to work together on supplying technical costs for Explore Art inc. deinstall

- Heritage Learning will still be doing ongoing activity for the under 5’s throughout – marketing to go in with our comms as one overall offer but all costs are covered for running those sessions