| Assessment of: | Substance: Future Forum | Assessment carried out by: | Carys Tavener |
| --- | --- | --- | --- |
| Assessment number: | 001 | Position: | Junior Production Manager |
| Date: | 14/11/17 | Review date: | 04/12/17 |
| Humber Street Gallery, HU1 1TU Fruit, HU1 1TU 1 @ The Dock, HU1 1UU C4Di: Theatre, HU1 1UU Hull Minster, HU1 1RR |  | Sections: 1.0 Production 2.0 Venue & Fire 3.0 Audience & Public HPSS – See attached |  |

| No. | ACTIVITY & WHO IS AT RISK | HAZARDS PRESENT | EXISTING CONTROL MEASURES | No. at risk | Risk factors |  |  | FURTHER ACTION REQUIRED & BY WHOM | DATE OF ACTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Likelihood | Severity | Risk Level |  |  |
| 1.1 | Loading equipment in/out Crew | Trip Hazards Potential Outcomes: Trips, minor physical injury | Clear path made to venue space Suppliers responsible for tying and storing all items away safely and appropriately | 9 | 1 | 2 | LOW | Please refer to supplier’s H&S documentation | 06.17.17 - 07.12.17 |
|  |  | Manual Handling Potential Outcomes: Spinal, muscular, physical injury | Contractors responsible for providing employees with manual handling training and PPE. Only those trained and competent to handle equipment | 9 | 2 | 3 | LOW | Please refer to supplier’s H&S documentation | 06.17.17 - 07.12.17 |
| 1.2 | Installing temporary electrical items Crew | Faulty or incorrect set-ups Potential Outcomes: Electric shocks and consequences of shocks e.g. falls | All equipment to be PAT tested Only trained and competent persons to install items Suppliers responsible for providing competent and trained persons to install equipment Suppliers responsible to check for any visual faults before using electrical items | 9 | 1 | 4 | LOW | Please refer to supplier’s H&S documentation | 06.17.17 - 07.12.17 |
| 1.3 | Installing fixtures onto temporary stands Crew and public | Unsecure items falling from height Potential Outcomes: Serious physical injury from falling projectiles | Only those competent and trained are to rig at height Items positioned at height to be secured with safety chain Weight and number of fixtures not to overload bars | 9 | 1 | 5 | LOW | Inspection of item's security checked by more than one crew member Supplier responsible for providing competent and trained persons | 06.17.17 - 07.12.17 |
| 2.1 | Fire & Emergencies | Emergency Evacuation Potential Outcomes: Panic, delays of time, severe physical injury | Venues existing fire evacuation procedures are to be followed CT to brief all Venue Event Managers prior to work Event Managers given notes and time on site prior to event to familiarise themselves with exits and assembly points |  | 1 | 5 | LOW | Please refer to attached Venue Event Manager Handbook with information given prior to festival All fire escape routes to be kept clear at all times House lights raised to full in the event of emergencies | 07.12.17 |
| 2.2 | Activity occurring in public environment (Humber Street Gallery + C4Di) Members of the public | Untrained and inexperienced persons present for production activity Potential Outcomes: Public nuisance and irritation, slight physical injury | Venue to inform staff of production activity As much activity as possible to be restricted to the event area |  | 3 | 1 | LOW | Suppliers and Venue to ensure clear access to usual business routes Venue to notify public of area of work with restricted entry | 07.12.17 |
| 2.3 | Refreshments provided for panelists and delegates All staff and public | Excess waste in venue spaces Potential Outcomes: Public nuisance and irritation | Venue Event Manager and volunteers to assist Venue with waste collection and disposal following the event CT to provide waste units in 1 @ The Dock |  | 1 | 1 | LOW |  | 07.12.17 |
| 2.4 | Hired temporary seating in 1 @ The Dock All staff and public | Unfamiliar egress and obstructions in emergency evacuation Potential Outcomes: Falls and accidental collisions, panic and delays in evacuation | Venue Event Manager will familiarise themselves with the auditorium as well as designated volunteers to direct audiences around specific routes Seatways positioned not less than 400mm wide and gangway no less than 1100mm wide Route to fire exit kept clear at all times and indicated in a show-stop Cable ties on chairs in rows of more than four |  | 1 | 5 | LOW | First Aid will be contactable by radio at all times Adequate lighting for public’s visibility during access and egress will be set All house lights raised in an emergency situation Volunteers to be positioned in the auditorium to alert audiences to hazards | 07.12.17 |
| 2.5 | Number of audience interest in panel over venue capacity allowance All staff and public | Venue over safe capacity for emergency egress Potential Outcomes: Falls and accidental collisions, panic and delays in evacuation | Venue Event Managers to give volunteers capacity counters to ensure the numbers of those attending remains within the limit |  | 1 | 5 | LOW | First Aid will be contactable by radio at all times Venue Event Managers to encourage those unable to attend to attend another panel | 07.12.17 |

RISK MATRIX

| LIKELIHOOD LIKELIHOOD SEVERITY SEVERITY | 1. Very unlikely (no known history) | 2. Unlikely (unlikely sequence of events) | 3. Possible (Foreseeable under unusual circumstances) | 4. Likely (Easily foresseable – some incidents may have occurred) | 5. Very likely (Common occurrence – aware of incidents) |
| --- | --- | --- | --- | --- | --- |
| 1. Negligible (no visible injury – no pain) | LOW | LOW | LOW | LOW | LOW |
| 2. Slight (minor cuts or bruises – no long term effects) | LOW | LOW | LOW | MEDIUM | MEDIUM |
| 3. Moderate (Heavy bruising, deep wounds, lost time) | LOW | LOW | MEDIUM | MEDIUM | HIGH |
| 4. Severe (Major injuries, lost time accidents, RIDDOR reportable) | LOW | MEDIUM | MEDIUM | HIGH | HIGH |
| 5. Very Severe (Long term disability or death) | LOW | MEDIUM | HIGH | HIGH | HIGH |

| NAME OF ASSESSOR: | Carys Tavener | DATE OF ASSESSMENT: | 14.11.17 |
| --- | --- | --- | --- |
| SIGNATURE: |  |  |  |
| CONTACT DETAILS |  |  |  |
| EMAIL: | carys.tavener@hull2017.co.uk | PHONE: | 01482 318860 |