Hull 2017/Blade

Rev. Indicative Cost Estimates AK 150816

| Description | Notes | Estimate | Rev Estimate |
| --- | --- | --- | --- |
| 1.Costs to date Arup Feasibility Study NK Artist Fee & Expenses 2.Transportation/SF Removal Advance Removal/Replacement of Street Furniture Install: 3nr teams night of transport, labour, vehicles & equipment Removal: 3nr teams night of transport, labour, vehicles & equipment 3.Support Structure Root, tip & passive ‘barriers’ 4.Installation Trial Installation (labour, plant, materials) Security/Pedestrian Control Street Cleaning Lighting Route security & Police attendance, delivery & removal 5.Display, Maintenance & Security Pressure Wash Cleaning Security 24/7 PC for ‘reactive’ maintenance Disposal/Making Good 6.Fees Artist Commission Fee (inc. expenses) Structural Design, Consents, H&S, Project Management Contingency TOTAL | Aalborg expenses in addition to fee Costed on basis of detailed route survey, items ‘required’ ? Allowance for ‘possible removal’ @ 50% New Year’s Day working Rev Est. reduced by 20% Rev E reduced by 20% Rev E reduced by 20% Rev E reduced by 70% Rev E reduced by 50% Rev E reflects update from NK Estimate x 13, Rev E x 4 Rev E reduced by approx. 50% Rev E reduced by 20% Ex 1 ‘Costs to Date’ – 5% | £17,850 £3,000 £79,800 £45.500 £30,600 £28,000 £76,200 £7,500 £23,300 £10,000 £1,000 £2,500 £30,000 £10,400 £49,140 £5,000 £5,000 £70,000 | £17,850 £3,626.11 £21,476.11 £79,800 £30,600 £28,000 £138,400 £61,000 £61,000 £6,000 £18,700 £3,000 £500 £3,000 £10,000 £41,200 £3,200 £25,000 £5,000 £5,000 £38,200 £13,000 £55,000 £68,000 £17,340 £17,340 £385,616 |