Assemble Fest Debrief: 12.06.2017

Bex Phillips, Maddie, Claire Drury, Nicci Halifax, Martin A

OSOS:

Traffic:

- Possibly bigger signs for bus stops.

License:

- Would go for a larger premises license for the whole road.

Tech:

- Sounds issues with the band.

- Needed to match up sound engineer with band.

- The shows was a lot shorter because crowd moved a lot quicker than anticipated.

Businesses:

- Reporting the busiest day of trade they’ve had all year.

Feedback Postcards:

- People wanting it to be a 2 day event.

- Larkins stayed open until midnight but could have gone later.

- Doing it over the bank holiday weekend would benefit.

Creative:

- Theatre companies aren’t spending enough time on developing the work or using the space.

Mentors:

- Gemma Kerr wasn’t great.

- Rash Dash were difficult to pin down.

- Petra Spymonkey and Hull Carnival Arts were a great match.

- Alan Lane great with Brick by Brick.

- Nick Barnes and Anna from Indigo Moon were a good match.

- How do you not spoil companies but also develop them?

  - Tighten up contracts.

Partnership/Funding:

- Larkins going to continue selling beer that Assemble Fest get a share of.

- Find the group of partners that don’t fit into our funding partners.

- Heritage Funding: a lot more reporting. Still finishing the project. Feels like it was worth the £17.5k

- Pete Massey went and loved it.

Marketing:

- Last year with this marketing manager. Need someone who can get he message out about the working with businesses and the arts.

What would you change:

- Box office.

- Sightlines for OSOS.

Future of Assemble Fest:

- Unlikely Maddie running it next year.

- Unlikely to be Bex working on it next year.