R1BW Internal Meeting Minutes
27/03/2017

Attending:  Chris Clay, Melissa McVeigh, Helen Thackeray, Jonathon Black, Rebecca Clark

| POINT | ACTION |
| --- | --- |
| 1. UPDATES |  |
| CC - Roach to be contracted ACTION: MM to liaise with JB and WH about Roach service agreement HT – Margaret Nieke to sign list off this week before continuing with contracting JB - meeting Roger at Beverley 28/03/2017 CC – meeting with MOD to confirm Leconfield as a Park & Ride site. Once this is confirmed there is no use for Hedon CC – Clarity around Burton Constable Holiday Park, is this managed by Rodrica Straker? HT confirmed not, land is managed by a tenant ACTION: HT to arrange a meeting with the holiday park CC - ordering wristbands and car mirror hangers (to fit in C5 envelopes) ACTION: MM to order these by 12/04/2017 CC – Welfare Management plan ACTION: MM to produce on Welfare Management plan JB & HT - meeting with Martin Walker, Civic One, on 28/03/2017 to discuss CCTV ACTION: HT to invite Andy Burton to CCTV meeting MM – to speak to MJ about unit price for the meals MM – meeting Gallowglass 28/03/2017 at 13:00. ACTION: MM to invite JB and HT HT – Queries about resident tickets. HT to set the parish meetings once the decision has been made. ACTION: CC/HT/JB to do a drive round 28/03/2017 | MM HT MM MM HT MM CC/HT/JB |