## 17.10.17
Back to Ours
Net contribution | 336250
Revised ticket sales | 40560 | Original ticket income was £53,148, difference of £12,588
total available to spend | 376810
Actual spend to date:
Feb 17 Festival | 44887
May 17 Festival | 78112 | Increaased £4,227 re Robertsons invoice for venue hire
Remote box office | 6300
Core | 19657 | £12,058 relates to Feb 17, £3,694 relates to May, balance relates to Oct
148956
Available for Oct 17 and Feb 18 festival | 227854
Forecast for Oct 17 festival | 97530 | As at 17.10.17
Potential amount left for Feb 18 Festival | 130324

## 17.11.17
Back to Ours
Net contribution | 336250
Revised ticket sales | 40560 | Original ticket income was £53,148, difference of £12,588
total available to spend | 376810
Actual spend to date:
Feb 17 Festival | 56945
May 17 Festival | 83660 | Includes £2,345 cost to be journalled here from Digital
Remote box office | 6300
Other Core | 2711
149616
Available for Oct 17 and Feb 18 festival | 227194
Forecast for Oct 17 festival | 99571 | As at 17.11.17
Potential amount left for Feb 18 Festival | 127623
Forecast amount to move to salaries re Feb 18 festival | 10000
Avaialble to spend on Feb 18 Festival | 117623
Note on B11: Kirsty Sutcliffe: £12,058 is from core costs
Note on B12: Kirsty Sutcliffe: £5,819 is core costs

## 11.12.17
Back To Ours
Hull 2017 contribution |  | 336250
Less transfer to salaries |  | -943
|  | 335307 | Agrees to budget grouped schedule
Actual ticket sales:
2017-02-01 | 10892
2017-05-01 | 9858
2017-10-01 | 10156
Projected ticket sales Feb 18 | 9905 |  | To adjust this on advice of Lou/Katy
|  | 40811 | Originally told Arts council that ticket sales would be £53,148
Total available budget |  | 376118
Summary:
|  | Cost | Contribution to cost (ticket sales) | Net
C700 (Feb & May 17) |  | 141090 | 20750 | 120340 | Project code closed
C701 (Core & Dev) |  | 8626 | 0 | 8626 | Project code closed
C727 (Oct 17) |  | 99571 | 10156 | 89415 | To close once all October actual costs have been received. If actual cost is greater or less than £99,571 move difference to C728
C728 (Feb 18) |  | 126831 | 9905 | 116926
|  | 376118 | 40811 | 335307
Secondment costs agreed with Goodwin for Feb 18 festival, £7,949 therefore budget currently available for Feb 18 festival is £118,882 (please note if projected ticket sales are lower than £9,905 then this amount will decrease)