Safety Briefing for ESAG

(Hull Filming only)

The following outlines our filming intentions and any specific safety requirements we will put in place.

Overall Notes:

Industry standard Risk Assessments, Movement Orders and Call Sheets will be produced throughout the shoot period and distributed to all crew and cast where appropriate.

Each person, cast or crew, will be sent a daily Risk Assessment specific to each day and location throughout the shoot period. The Lead Producer and 1st Assistant Director will produce and sign off on each Risk Assessment.

Turnaround Time – All cast and crew will be given a turnaround time of 11 hours from wrap until call time each day.

Transport will be coordinated by the production team.

All locations will have access to toilets and amenities within walking or car shuttling distance.

When necessary all crew will be made aware of fully working locations and told to respect the public accordingly.

Radios will be used at all times for both communication and safety.

Production will adhere to the specific Safeguarding policy put in place by Blast Theory and agreed by Hull 2017.

Day by Day:

DAY ONE:

New City Plot – Bishop Burton

Humber Marshes – Water Ski Club

Crew Numbers:	25

Cast Numbers:	3

Exterior filming. Be aware of weather.

No special requirements.

DAY TWO:

Humber Bridge

Humber Bridge Anchorage

Crew Numbers:	25

Cast Numbers:	5

Extras:		12

Exterior filming. Be aware of weather.

Interior Anchorage needs a specific procedure to get all kit down to the bottom using a pulley system. Humber Bridge company have been engaged to provide safety support and a member of staff will be with us at all times.

Only 25 members of the team (cast and crew) will be allowed in the anchorage at any one time.

Additional: Press visit will be schedule for this day at 8am.

DAY THREE:

Salt End, Paull

Humber Marshes, Water Ski Club.

Crew Numbers:	25

Cast Numbers:	6

Exterior filming. Be aware of weather.

Actors will enter water -  Additional safety elements will be put in place for this stage of filming, wet suits, warm location after filming (with shower)

No under 18 actors will enter water.

DAY FOUR:

Minerva Pier

Amiral’s Steps

Crew Numbers:	25

Cast Numbers:	7

Exterior filming. Be aware of weather.

All crew of the admiral steps will adhere to the location protocol of wearing life-jackets. When Cinematographer is unable to do so due to camera restrictions a spotter will be provided.

DAY FIVE:

Preston Road Estate

New City, Bishop Burton College

Crew Numbers:	25

Cast Numbers:	5

Exterior filming. Be aware of weather.

Public may be present and additional AD’s will provided to manage this.

No special requirements.

DAY SIX:

Interior Apartment, Wlikonson House, Doncaster.

Interior location, respect must be given to owner and the safety of his belongings.

Black Out curtain will be used on windows. Ladders to be provided and used according to health and safety regulations.

Location Details:

New City Plot

Bishop Burton College

Address: York Rd, Bishop Burton, Beverley HU17 8QG

Contact: David Drury - 01964 553000

Parking: park through the main college entrance.

Humber Bridge: Surrounding Areas and Foreshore.

1st stop: Humber Bridge Car Park, Cliff Road

2nd stop: Humber Bridge Board, Ferriby Road, Hessle, East Yorkshire, England, HU13 0HX

Contact: Martin Davis - 07751997769

Parking: Approach the Humber Bridge Board, at the barriers buzz and say you're there to see Martin Davis.

Humber Bridge Anchorage

1st stop: Humber Bridge Board, Ferriby Road, Hessle, East Yorkshire, England, HU13 0HX

Contact: Martin Davis - 07751997769

Parking: Approach the Humber Bridge Board, at the barriers buzz and say you're there to see Martin Davis.

Salt End Field

Paull Road, Paull,

Parking: No parking, we will be ferrying people from nearby rugby club.

Marshes

Humber Marshes/Water Ski Club, Barrow-upon-Humber DN19 7HA

Contact: Tony Green

Parking: Free to park on grass next to clubhouse

Admiral's Steps/Pier

Minerva Pier, Hull HU1 1UZ

Contact: Pete Curry - 07831725953

Parking: Free parking up to 2 hours and will sort permits beyond this.

Preston Road Estate

Contact: Pete Curry - 07831725953

Parking

Interior Apartment

Wilkinson House, 3a Ellers Road, Doncaster, South Yorkshire, DN4 7BE

Contact/Owner: Bryden Rimmer - 07891 964631

Parking