## Sheet1
LGBT 50 Milestone Plan | Milestone date (delivery) | Other End Date (if reqd.)
Pride in Hull |  |  | Contract Dates
Proposal and Budget (H2017) | 2016-11-18 |  | Plan Dates
Venue, Event site, Parade Route | 2006-12-01 |  | Event dates
Marcomms Plan (BLF) | 2017-01-01
Contract (H2017) | 2017-01-13
Progress Report (BLF) | 2017-03-15
Film and Songwriting competition | 2016-09-01 | 2017-03-31
Site Safety, First Aid, Security, ESAG | 2006-10-01 | 2017-03-31
Sponsorship promotion and sales | 2016-10-01 | 2017-03-31
Headline artist booking | 2016-12-01 | 2017-03-31
Small venue booking | 2017-01-01 | 2017-03-31
Tech and toilet hire | 2017-01-01 | 2017-03-31
Local and other artist booking | 2016-01-01 | 2017-05-31
Community market engagement | 2017-01-01 | 2017-05-31
Event Dates | 2017-07-22 | 2017-07-26
Marketing/PR plan | 2017-01-01 | 2017-07-29
Volunteer programme | 2017-01-01 | 2017-07-29
Final project report (BLF) | 2017-08-15
Final Report (H2017) | 2017-08-15
Duckie
Yorkshire Dance
BBC
Note on A7: Smyth Cian (2017): (Updates on project delivery plan, timeline, marcomms, budget) Monitoring and evaluation Baseline