Hull Legacy Project

We hope to create an exciting new piece which will offer an opportunity for participants involved in the NMB Composer Residencies to continue their involvement in creative music-making and also bring on-board new participant groups.

The piece will be modular in order to accommodate a range of participants and abilities.  In response to how much time each group is able to commit to the project James will create parts to fit.

The piece will be generated during 6 days of creative workshops at the start of the Autumn Term.  James will then take away the raw materials and stick them together as well as orchestrate the piece for the instrumentalists.  Early in Spring 2018 we will have a launch event to introduce the piece to the teachers and music leaders who will be responsible for overseeing the learning of the piece.  It might be worth having a mid-term joint rehearsal day to keep momentum and build excitement.  The performance will be at the end of the Spring Term or early in the Summer Term.

James’ 28 remaining days will be spent as follows:

6 days of creative composition workshops (possible dates include: September 4-5; 7-8; 11-12; 14-15; 21-22)

16 days of homework arranging the material and orchestrating it for participant groups

1 launch day (23rd January)

1 mid-term joint rehearsal day (23/24 Feb)

4 days of rehearsals and performance (Dates TBC)

Some questions:

- If the music service are interested, when would their ideal performance slot be?

- Can we involve James from the CPD and his independent school in the performance somehow?  Can he be released by his school to visit local state primaries and teach them the material?

- How do we support Hull Uni students to be more involved?

- Do we have CPD sessions for when I’m up doing creative workshops?  If so, what function do these fulfill?   Are they a talking shop for peer-support?  A surgery where people can bring specific questions or challenges?  An opportunity for people to come and practice leading exercises in front of a sympathetic group?