## Sheet1
JUNE
| m | t | w | t | f | s | s
|  |  |  | 1 | 2 | 3 | 4
| 5 | 6 | 7 | 8 | 9 | 10 | 11
PID completed
| 12 | 13 | 14 | 15 | 16 | 17 | 18
Greenlit
| 19 | 20 | 21 | 22 | 23 | 24 | 25
| Premise license deadline |  | Pearson Trustees decision received |  | Jan Neats Site Visit
| 26 | 27 | 28 | 29 | 30
|  |  |  | FEU submitted | Event management draft plan completed (Tim)
All delivery documents received and 2nd instalment 15% of fee released
JULY
| m | t | w | t | f | s | s
[6 empty] | 1 | 2
| 3 | 4 | 5 | 6 | 7 | 8 | 9
| 10 | 11 | 12 | 13 | 14 | 15 | 16
| 17 | 18 | 19 | 20 | 21 | 22 | 23
Amend Ibis Booking
| 24 | 25 | 26 | 27 | 28 | 29 | 30
31
AUGUST
| m | t | w | t | f | s | s
|  | 1 | 2 | 3 | 4 | 5 | 6
Adam arrives
| 7 | 8 | 9 | 10 | 11 | 12 | 13
|  |  | CirkVOST arrive | Get in | Get in | EPICYCLE 21:00 | EPICYCLE 21:00
Adam site person arrives
| 14 | 15 | 16 | 17 | 18 | 19 | 20
| Get out | 1: Get out; 2: Final CirkVOST leave
| Adam site person leaves | 1: Adam leaves
| 21 | 22 | 23 | 24 | 25 | 26 | 27
| 28 | 1: 29; 2: 30; 3: 31