Slung Low: 04.11.2016

Update:

- Sodium doing Prologue.

- Whitby filming. Slung Low company staying on the boat.

- Slung Low’s glass water tank for under water filming.

- Airstream Caravan: finished and completed car park caravan list. Joanna to send list over. Converting the caravan in to 6 seater cinema. 5 mins max.  36 people an hour. 10 mins turn around. There 6 hrs a day.

- Volunteers: offered but not required. Let me know if this changes at all.

- The prologue will also exist on the internet and Slung Low will hand out business cards. Not wheel chair accessible, but will have viewing screen for this outside the caravan.

- Need to cast Glorianna now: need to find a fee structure. Someone just come out of Manchester drama school looks like a possibility.

- Person profile: Need to be young,

- Look like they are from country’s such as: Egypt, Syria, Libya, or nearby nations.

- Need to be physically fit due to the nature of the work.

Ticket Pricing:

- We will charge and then strategically target.

- Work through a suggested formula with David. £10-£15 tickets.

- Difficult to budget the income for pay what you can.

- Use Back to Ours to target some ticket sales possibly.

- Get sums back to you by the end of November.

Part 2: April live Performance.

- First draft is in.

- Quite political.

- Moves it away from disaster movie.

Performance live: part 3:

- Treatment received.

- 1 July: BBC performance live. Live to tape – need to overlay some bits.

- Al to have a conversation with Jonti.

- Approved by the Space, but BBC and Space funding can’t really collide. Finding a work around for this.

Marketing:

- On sale date: Jan 23 not feasible because of BBC. Maybe shift this back a week.

- First cut of prologue: 20 Feb possibly?

- Make a decision by the end of November with regards to ticket price.

- Teaser should be available after 10/11 Jan.

- Pushing this as online, on television and near you in communications.

- It is a ground breaking theatrical performance, performed live, online and on television in 4 parts. We should go for this – no one has done this. This informs PR conversation with cornershop.

- Al package up everything for the brochure.

- Newsletter for Victoria dock residents, info for December.

- MA to arrange the meeting in leeds/hull with cornershop. What will cornershop do?

Access:

- Pick up the conversation with the new company who have been awarded tender.

- MA to receive most up to date schedule from Joanna.

License:

- 9 January: deadline for License application.

- Gareth to apply – Slung Low to fill out template that Gareth sends over.

- MA to follow up who will put the bar in to the Victoria Dock site.

- Get license for regular entertainment, attach a TEN to it for alcohol.

- Gareth to confirm ESAG diary. Then we will explore special permissions for Helicopters, etc.

Other:

- Testing the waters in first week of January. This will be the first presence of Slung Low on site. They might BBQ for everyone.

- Middle of December: Victoria dock residents’ association.

- Need access to the power and that will save thousands.

Things to ask:

- Vulnerable adults/people training: Slung Low have you had this? It’s something our council colleagues can help with in terms working with community cast and inviting people into airstream caravan. Might not be a bad idea?

Errollyn Wallen:

- PRS New music biennial artist, working with refugee groups to create a new performance for 2017. Potential connection if Slung Low feel like they might like to make it at all?