## Running Order
TIME | ACTIVITY | VENUE |  | CONTACT
MONDAY 4 DECEMBER
08:00 tbc | BBC Rig | Hull Minster
TUESDAY 5 DECEMBER
TBC | BBC Rig | Ferens Art Gallery | Gallery closed to the public
TBC | BBC filming | Ferens Art Gallery
10:00 | Jury (x 10 people) begin deliberation | Maritime Museum | Lunch and refreshments from Nibble to be provided at 13:00 tbc | Lily Mellor | PRESS
18:00 | Drinks Reception | Ferens Art Gallery | Hold private space for artists in upstairs gallery
18:00 - 18:30 | ITV Calendar Live | Ferens Art Gallery? |  | Ben McKnight
18:30 | BBC Look North Live | Ferens / Minster | 2 separate presenters at each venue Confirm 1 x curator doing tour with presenter at Ferens | Ben McKnight / Eimear McNamara | HPSS get-in/out
19:15 | Guests escorted to the Minster | Ferens Art Gallery | Hull 2017 Volunteers to assist |  | Saunts get-in
19:15 | BBC set-up | Ferens Art Gallery |  | Melanie Fanstone | Movement between Ferens > Minster > HSG
19:30 | Guests arrive | Hull Minster | Guests given drink on arrival, but shown directly to table
19:45 | Guests seated, welcome speech | Hull Minster | Martin Green to deliver welcome speech |  | PRESS, e.g.photographers escorted to winners room
19:50 | Cold starter served | Hull Minster |  |  | Will Gompertz location
20:15 | Clear Starter | Hull Minster |  |  | Artist wrangler
20:25 | Serve Main | Hull Minster |  |  | Curator wrangler
21:00 | Clear Main | Hull Minster
21:10 | Serve cold dessert & coffee | Hull Minster | Coffee cups given our when pudding served. Coffee brought round later |  | Seating plan at Ferens/Minster
21:30 | Go Live | Hull Minster | MG to be interviewed as part of programme rather than give speech |  | Wristband distribution
21:40 | BBC News live | Ferens / Minster | 1 x presenter at each venue
21:41 | Speech 1 - Tate | Hull Minster
21:45 | Speech 2 - Goldie | Hull Minster
21:49 | Speech 3 - Winner | Hull Minster
21:56 | Programme Ends | Hull Minster
22:00 | Winner travels to Ferens | Hull Minster | Route TBC (weather dependent) - walking or by car
22:00 | Clear Dessert and Coffee | Hull Minster
22:10 | Winner live on BBC News at 10 with Will Gompertz | Ferens Art Gallery
22:35 | Winner live on BBC World Tonight | Ferens Art Gallery
22:?? | Winner live on BBC Radio 4 | Ferens Art Gallery
22:30 | Guest leave venue | Hull Minster
22:30 | Winner taken to afterparty venue | Humber Street Gallery
23:00 | Clear Venue | Hull Minster
TATE CONTACTS
BBC CONTACTS
BBC GUESTS
PRESS ATTENDING DINNER
PHOTOGAPHERS

## Milestones
MILESTONES |  | NOTES
2017-10-16 | Deadline for Artist's Lists
2017-10-19 | Deadline for Tate guestlist
2017-10-25 | First wave of invites go out
2017-11-10 | RSVP deadline for first wave
2017-11-13 | Second wave of invites go out
2017-11-23 | RSVP deadline for second wave
2017-11-30 | Notify Saunts of guest and supplier meal numbers
CATERING | Confirm menu with Saunts | JH to set meeting with caterers
| Put order in with HOT | JH to book wine, Saunts to deliver
| Wine for Ferens Reception | JH to order
VENUES | Exterior lighting for both venues
| Afterparty location | JH to book
| Winner transport to Ferens for News at 10 | 2017 staff to manage - who tbc
BBC - room for staff/breakout area
| Confirm press with BM - Room for filing | For schedule & guestlist
PRODUCTION | Production milestones | Design, lighting, AV, dressing
| Production Schedule | BBC/HPSS/Saunts/Furniture
| Confirm portaloos | RC to research
| Confirm wristbands | RC to research
| Speeches | off-air, on-air
| Press - interview schedules | BM
Do we need content on screen?
Running Order
STAFFING | Volunteer ask & locations | Ferens, way finding, cloakroom at Minster
| Staff roles (wrangling artists/curators) | Stage Manager, who tbc
BSL interpreter tbc
| Press wrangling | Will Gompertz requirements
AOB | Goldie
| Steve Cobby DJ for the night | Spec tbc
PDF Invitation can be circulated?
Budget