LOGG FORTNIGHTLY ACTIVITY UPDATE

|  | PUBLIC FACING EVENTS/MOMENTS | INTERNAL | PRESS | DIGITAL | OTHER |
| --- | --- | --- | --- | --- | --- |
| Monday 3 July |  |  | HDM prints article with pic of Re-rediff in outfits going out to collect voices for project VEAR. Call out for social gatherings. | GGF report on forming a pub quiz team with Re-rediffusion |  |
| Tuesday 4 July | Project VEAR voice collecting |  |  |  |  |
| Wednesday 5 July | GNGG Project VEAR voice collecting | Davy and Rosie site visit | Article in HDM about The Longhill Burn and backstory. | Fellowship post update about Longhill. |  |
| Thursday 6 July | GNGG Project VEAR voice collecting Large crate with The Longhill Burn event info and LoGG Stamps appear in Longhill | LOGG weekly catch up LOGG budget catch up |  |  |  |
| Friday 7 July | GNGG |  |  |  |  |
| Saturday 8 July | GNGG |  |  |  |  |
| Sunday 9 July | GNGG |  |  |  |  |
| Monday 10 July | And Now: engagement activity |  |  | GGF posts about activity in Longhill |  |
| Tuesday 11 July |  |  |  |  |  |
| Wednesday 12 July | GNGG Project VEAR voice collecting And Now: engagement activity |  |  | GGF posts about activity in Longhill |  |
| Thursday 13 July | GNGG Project VEAR voice collecting And Now: engagement activity | LOGG Ambassador volunteer training, Longhill |  |  |  |
| Friday 14 July | GNGG Project VEAR voice collecting Large stack of crates appears outside Eastmount Community Centre in Longhill. | And Now: production meeting |  | GGF posts about activity in Longhill |  |
| Saturday 15 July | GNGG Project VEAR voice collecting And Now: The Longhill Burn |  |  |  | Periplum RSVP’d to attend bonfire. |
| Sunday 16 July | GNGG Project VEAR voice collecting |  |  |  |  |

Updates

Lone Twin are no longer involved in Land of Green Ginger. And Now: have taken over the project.

Joshua is having a hard time with volunteer numbers. We are looking at alternative ways to keep the shop staffed.

Slowly approaching contract stage with Macnas, as we’ve received their budget

Aswarm have their first set of voice collecting next week, and have also had their share of challenges around volunteering shifts.

Key Dates:

17 June: Gold Nose of Green Ginger shop opens at North Point

3 – 6 July: Project VEAR voice collection

12 – 16 July: Project VEAR voice collection

10th, 13-14 July: And Now: community activity in Longhill

15 July: And Now: The Longhill Burn

19 August: Gold Nose of Green Ginger closing procession at North Point

6 – 9 September: Project VEAR voice collection

22 – 30 September: Project VEAR live at Pickering Park

20 October – 5 November: Cardboard City live at Springhead Pumping Station

11 November: Macnas parade in Old Town