## Workstreams_v1
Time | Work Streams
| PM | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 | Team 10 | Team 11 | Team 12 | Team 13 | Team 14 | Team 14
|  | Projection Team | Cleansing Team | Security and Crowd Control at QVS | Cranes | Supports | Ballast | Police Escort | Blade | Signals (2 gangs of 3 ppl) | A63 Lighting (1 gang of 4 people) | Hull City Center Lighting & signals (2 gangs of 3ppl) | Traffic Management | Press | Volunteer Parade | Refreshments (example- needs adding) | Assumptions
| Org | Hull CC 2017 | Hull CC 2017 | Hull CC 2017 | ALE | DB Engineering | Central Cranes | Hull Police | ALE | North Midlands | North Midlands | North Midlands | North Midlands | Hull CC 2017 | Hull CC 2017
| Name | Chris Clay | Chris Clay | Chris Clay | Dave Smith | Darren B | Jamie Chan | PC Darren Storr | Dave Smith | Jon Hudson | Jon Hudson | Jon Hudson | Jon Hudson | Ben McKnight | Ben McKnight
| Mobile | 7771 788221 | 7771 788221 | 7771 788221 | 7391 512990 | 07790 666002 | 07446 188 661 | 07919 690101 | 7391 512990 | 7968 766603 | 7968 766603 | 7968 766603 | 7968 766603 | 07718 100793 | 07718 100793
20:30 |  | Team 5: Tip supports loaded the night before; Team 8: Blade loaded onto transport system
20:40
20:50
21:00 |  | Team 1: Event Finishes; Team 3: Start stewarding the public out of QVS
21:10
21:20
21:30 |  | Team 3: Start putting up crowd control barriers around QVS | Assume the safety and team briefings will be done within 30mins- can give 1 hour as a buffer.
21:40
21:50
22:00 | QVS is clear | Team 1: Designated area around Monument for derigging; Team 12: Southbound Road closure on Market Place; Team 14: Team 3 on rolling breaks | Assume it takes cranes/ lorries 30mins to travel from the docks to QVS.
22:10
22:20
22:30 |  | Team 2: Empty bins
22:40
22:50 | Cranes at QVS | [15 empty] | Assume QVS is secure within 50mins of starting to put barriers up
23:00 |  | Team 2: Leave QVS; Team 11: Turn 2: Lighting and signs removed
23:10
23:20
23:30 | Kick off for Named team leads | Team 5: Two hi-abs with tip support and root sets off to QVS
23:40
23:50
0:00 | Offload tip support | Team 1: Partial possession for Blade teams; Team 5: Arrive at QVS and offload sections; Team 9: Turns 6 & 7: Switch from permanent to temporary signals; Team 12: TM on Turns 5, 6 & 7
0:10
0:20
0:30 |  | Team 5: Start Assembling tip support with transport hi-ab; Team 14: Team 4 on break | Assume Pearl Green able to drill holes for supports
0:40 | [16 empty] | Assume Pearl Green able to drill holes for supports
0:50
1:00 | Blade sets off from Alexander Docks | Team 6: Crane company starts delivering ballast to QVS and stockpiles them adjacent to tip support; Team 7: Set off from Alexander Docks to QVS- leap frogging; Team 8: Blade sets off from Alexander Docks; Team 11: Turrn 7: Lighting and signs removed
1:10
1:20 | bar: Team 1 to Team 3
1:30
1:40
1:50
2:00 | Hourly catch up with all leads | Team 8: Exit turn 2; Team 9: Turn 4: signals removed; Team 10: Turn 4: Lighting removed
2:10 |  | Team 6: 2nd load delivered to site
2:20
2:30 |  | Team 5: Drill and resin fix bolts for tip support; Team 8: Exit turn 3; Team 13: Press Mount Pleasant (under flyover)
2:40
2:50
3:00 | Hourly catch up with all leads | Team 8: Exit turn 4; Team 9: Turn 5: signals removed; Team 10: Turn 5: lighting removed; Team 11: Turn 2: Lighting and signs reinstated; Team 13: Press on terrace at Premier Inn hotel; Team 14: Team 4 finish break; Team 9 on break | Assume projection team needs 5 hours for derigging
3:10
3:20 |  | Team 6: 3rd Load delivered to site
3:30 |  | Team 8: Start Turn 5; Team 10: Reinstate turn 4 lighting
3:40
3:50
4:00 | Hourly catch up with all leads | Team 3: QVS - full posession; Team 7: Blade off A63- vigilant of public; Team 8: Blade off A63 & arrives at Market Place; Team 10: Start reinstating A63; Team 13: Press on Queen Street /A63 corner; Team 14: Team 6 & 7 on break; Team 9 off break
4:10
4:20 |  | Team 6: 4th load delivered to site
4:30 | Blade leaves Market Place | Team 4: Set off to QVS; Team 5: Start loading on ballast for tip support; Team 6: Start loading on ballast for tip support; Team 8: Blade leaves Market Place
4:40
4:50
5:00 | Hourly catch up with all leads; QVS - full posession & Blade leaves A63 | Team 1: Leave QVS- potential for small work area near Maritime museum; Team 4: Arrive at QVS and start setting up; Team 8: From Turn 6 to Exit of Turn 7; Team 10: Turn 5: lighting reinstated; Team 11: Turn 7: Lighting and signs reinstated; Team 13: Press bus folllows convoy from Turn 6; Team 14: Team 6 & 7 finish break
5:10 |  | Team 6: 4th load delivered to site
5:20
5:30 |  | Team 5: Apply grout under feet
5:40 | Hand A63 to Highways England for inspection
5:50
| PM | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 | Team 10 | Team 11 | Team 12 | Team 13 | Team 14
6:00 | Hourly catch up with all leads; A63 is reopened to public | Team 4: Root crane set up at QVS; Team 9: Turn 6 & 7: Switch from temporary to permanent signals; Team 13: Siemens crowd and press at Carr Ln/Cross St | Team 4 & 5 on break
6:10 | Tip support is secure | Team 5: Tip support ready; Team 14: Staff (max 200) outside Maritime Museum
6:20
6:30 |  | Team 3: Close off roads to ensure that no pedestrians pass on Carr lane and under any lifting operations
6:40
6:50
7:00 | Hourly catch up with all leads; Blade arrives at Saville Street | Team 3: Be vigilant of anyone attempting to enter square; Team 7: Exit of Turn 7; Team 8: Exit of Turn 7; Team 12: FinishTM on Turns 5, 6 & 7; Team 13: Press at City Hall
7:10
7:20
7:30 | Blade manouvered into QVS | Team 4: Set up root crane; Team 7: Blade manouvered onto QVS- ready for lifting; Team 8: Blade manouvered onto QVS- ready for lifting | Team 4 & 5 off break
7:40
7:50
8:00 | Hourly catch up with all leads | Team 4: Lift blade off of the transporters; Team 5: Lift blade off of the transporters
8:10
8:20 |  | Team 4: Blade resting on ground to remove feet and attach feet; Team 5: Blade resting on ground to remove feet and attach feet; Team 7: Escort transporters back to Siemens; Team 8: Blade resting on ground to remove feet and attach feet
8:30
8:40
8:50
9:00 | Hourly catch up with all leads | Team 1: All areas on QVS clear; Team 4: Turn and lift up blade in the correct orientation; Team 5: Turn and lift up blade in the correct orientation; Team 8: Turn and lift up blade in the correct orientation; Team 9: Finished
9:10 |  | Team 5: Root support manouvered into place
9:20
9:30
9:40
9:50
10:00
10:10
10:20
10:30
10:40
10:50
11:00 | Catch up with all leads; Drop blade onto support and bolt feet onto top of root support
11:10 |  | Team 5: Root support manouvered into place
11:20
11:30 |  | Team 5: Load 9 tonne ballast onto root support
11:40
11:50 |  | Team 5: Bolt plate on top of root
12:00
12:10
12:20 |  | Team 4: Drop blade onto support and bolt feet onto top of root support; Team 5: Drop blade onto support and bolt feet onto top of root support; Team 8: Drop blade onto support and bolt feet onto top of root support
12:30
12:40
12:50 | Check blade is secure and in correct positon | Team 5: Ensure support is in right position; Team 8: Ensure support is in right position
13:00 | Catch up with all leads; | Team 5: Start drilling and resin fixing the bolts for the support; Team 8: Start drilling and resin fixing the bolts for the support
13:10
13:20
13:30
13:40
13:50 | Start packing away crowd control measures | Team 3: Start packing away crowd control measures
14:00 | Catch up with all leads; | Team 5: Root support secured in palce.
14:10 |  | Team 5: Pour grout under feet
14:20 |  | Team 4: Check blade is secure and in correct positon; Team 5: Check blade is secure and in correct positon; Team 8: Check blade is secure and in correct positon
14:30 | Hand QVS over to Hull City Council | Team 4: Release blade; Team 5: Release blade
14:40
14:50 |  | Team 4: Crane start derigging
15:00
15:10
15:20
15:30
15:40
15:50 |  | Team 4: Cranes leave QVS
16:00

## Sheet1 (2)
|  | Time start | Time finish | Time taken | Issues/ comments
Tip support- putting it together
Root support- putting it together
Manouver Past the tree/ crane/ light
Place tip tripod
Place root tripod
Lower blade
drilling 30 holes for clamp on tip support
drilling 16 holes to connect root support to clamp
Questions
1 | Can the blade track in if tip support in place?
2 | Can the blade can shift over and allow supports to be lifted in by cranes?
3 | Preferance for dirlling holes when supports are in place instead of drilling and then lifting supports off and back on again?
4 | Do the supports need to be put together on site?
5 | How long will it take?
6 | Does the ballast need to be added before the supports are assembled or after?
7 | How long to add ballast to supports?
8 | Therefore is ballast added prior to blade arriving on the square? (If it is, it will be harder to manouver)
9 | How long to drill and resin fix 24 holes (2 hours?)
10 | How long to fix the blade in position when it has been lifted in?

## phone list
Name | Number | Organisation
Sam Hunt | 7968855187 | Hull 2017
Helen Thackeray | 7943764755 | Hull 2017
Anthony Granville | 7808827235 | Siemens
Javed Hussain | 7880357245 | Arup
Milly Hennayake | 7823355657 | Arup
Richard Bickers | 7795815670 | Arup
Tony Shchultz | 7771770455 | Pearl Green
Graham Lownsborough | 7850251329 | HCC Highways Network
Dave Crossland | 7545643873 | Aone+ supervisor for A65
Tim Beekly | 7785520624 | HCC Trees Officer- on call
Andrew Knight | 7801260503 | Hull 2017