Larkin Exhibition
Fri 1st July 2016

Present: SW, JB, PP, GC, IR, HD, JT, SH 
Apologies:  MLS

Notes												Actions
Guest Curator:

Grayson Perry has passed this onto his agent - GC sent correspondence W/C 12/06

- Alan Bennet & David Walliams to be contacted						GC

Nick Cave would like to be involved. Names in the hat: Grayson Perry, Alan Bennett, David Walliams, Nick Cave, Lenny Henry.

Dates:

The National Portrait Gallery Exhibition has moved Apr/May/June.

- Larkin Festival should finish when the BBC Spoken Word Fest starts. (July-Sept)		MLS

Project Development:

Project outline has been shared

BBC:

Christine Hammel is possibly going to make a new BBC show, based on Larkin’s photos of Hull and the region.

- Could this programme coincide with the exhibition?					GC

- Larkin Exhibition to be flagged to the BBC (Pat Connor)					HD / SH

- A list of photos to be put together – what has been used previously and what has not?	GC

SW is keen to have a conversation with BBC about what they have in their archives		SW

Marketing & Audience Development:

Learning & Participation programme is contingent on who the guest curator is.

- How do we use current/make resource for A-level and GCSE students? 			IR

- Can we run a summer school? 								IR

- A MC&L representative to join the next meeting in July. 					HD / PB

- What is the family learning element of this project?					IR

- How can we re-connect Larkin with Local People?					IR

- How to we engage a wider interest in poetry?						HD

- Link this project to Freedom Fest, Why are we doing this at this time?			HD / SW

- Literary meeting on 21st July to be flagged to Larkin Society				HD / PP/ GC

- Cultural Visions at the Uni; this exhibition should be one of them			HD / SH

- Online map of Larkin Trails/Maps to be shared/created					HD / DW

- LARKIN TRAIL learning resource to be shared with IR					GC

Budget

- Workable budget to be put together							HD / SH / JT

HD to write job description for the Project Director (Look at DS Job description)			HD

Funding

- Larkin25 ACE application to be shared with JT						GC

- List of keys things to be pulled together for funding applications				JT

JT is not here from 8th till 15th July.

To be added to the next agenda: Next meeting – Thursday 28th, 11am till 12.30pm.

- What is going to be the name of the exhibition?