## Slide 1
NETWORK NEIGHBOURHOOD TOURING
2016
2018
Today
Jun
Sep
Dec
2017
Jun
Sep
Dec
Marker
1/6/2016
Pilot events programme confirmed
1/8/2016
Brand & MarComms plan confirmed
1/8/2016
Project Team start
1/9/2016
Hull 2017 Programme launch (inc NNT)
1/9/2016
F1: Programme launch & ticket release
1/1/2017
F2: Programme launch & ticket release
1/3/2017
F3: Programme launch & ticket release
1/8/2017
F4: Programme launch & ticket release
1/12/2017
608 days
1/7/2016 - 28/2/2018
Monthly Programming Team meetings
31 days
1/7/2016 - 31/7/2016
Local venue & project team recruitment
31 days
1/7/2016 - 31/7/2016
Brand & MarComms plan development
31 days
1/10/2016 - 31/10/2016
Pilot events (Half term)
30 days
1/11/2016 - 30/11/2016
F1: Programme confirmation
31 days
1/12/2016 - 31/12/2016
F1: Contracts issued
28 days
1/2/2017 - 28/2/2017
Festival 1 (Half term)
31 days
1/1/2017 - 31/1/2017
F2: Programme confirmation
28 days
1/2/2017 - 28/2/2017
F2: Contracts issued
31 days
1/5/2017 - 31/5/2017
Festival 2 (Half term)
30 days
1/6/2017 - 30/6/2017
F3: Programme confirmation
31 days
1/7/2017 - 31/7/2017
F3: Contracts issued
31 days
1/10/2017 - 31/10/2017
Festival 3 (Half term)
30 days
1/11/2017 - 30/11/2017
F4: Programme confirmation
31 days
1/12/2017 - 31/12/2017
F4: Contracts issued
31 days
1/1/2018 - 31/1/2018
Evaluation of Festivals 1-3
28 days
1/2/2018 - 28/2/2018
Festival 4 (Half term)