LOGG WEEKLY ACTIVITY UPDATE

|  | PUBLIC FACING EVENTS/MOMENTS | INTERNAL | PRESS | DIGITAL | OTHER |
| --- | --- | --- | --- | --- | --- |
| Monday 12 June |  |  |  |  | GNGG leaflets in the space for rehearsal period |
| Tuesday 13 June | All smaller crates are now gone. |  |  | GGF send 'teaser' photos of GNGG space out |  |
| Wednesday 14 June |  | LOGG away day |  |  |  |
| Thursday 15 June |  | LOGG MarComms meeting Lone Twin M&E catch up LOGG weekly catch up |  | GGF report - all crates now gone |  |
| Friday 16 June |  | Volunteer pre event briefings: 3pm and 5:30pm |  |  |  |
| Saturday 17 June | Gold Nose of Green Ginger opening ceremony |  |  | GGF report on the GNGG opening ceremony A Facebook event appears aboutthe GNGG. | Photographer taking photos for Mon HDM articles Doc filmmakers start filming |
| Sunday 18 June | GNGG open for business |  |  |  |  |

Updates

Lone Twin

- And Now: contract complete

-Discussions taking place regarding heralding activity

Davy

- Davy liaising with Garth West regarding new pumping station designs

Joshua

-Pamphlet getting printed

-RAMS completed

-M&E documentary confirmed with Electric Egg

-M&E discussions around audience surveys being confirmed

Thor

-GH working on KCOM sponsorship

-EB confirming volunteering shifts for voice collecting

-First week of voice collecting schedule nearly full (3-6 July)

Macnas

-KF to email Noeline re: next steps

Overdue

-Periplum’s final payment

-Walk the Plank’s final budget breakdown and final payment

-Lone Twin contract

Key Dates:

17 June: Gold Nose of Green Ginger shop opens at North Point

3 – 6 July: Project VEAR voice collection

12 – 16 July: Project VEAR voice collection

9 – 15 July: Guild of Commoners activity live in Longhill

15 July: And Now bonfire, Longhill

19 August: Gold Nose of Green Ginger closing procession at North Point

6 – 9 September: Project VEAR voice collection

22 – 30 September: Project VEAR live at Pickering Park

20 October – 5 November: Cardboard City live at Springhead Pumping Station

11 November: Macnas parade in Old Town