## Sheet1
Depart tour: Hull
DEPART by Circa - Choir SCHEDULE _ V1.2017
v1 | Activity | Time | Location | Notes
HULL | General Cemetery - Spring Bank West, HU3SE. Backstage at Thoresby Primary School
Friday, 12th May | 1830 - 2100 On-site Choir Rehearsal in Hull.Alice to attend. Access to Thoresby main hall grnd floor.
Sunday, 14th May | 1500 - 1800 Trail Guides + Choir Guides Rehearsal on-site
Monday, 15th May | 1800 - 2100 Trail Guides + Choir Guides Rehearsal on-site
Tuesday, May 16th | TECHNICAL REHEARSAL - Singing Guides & Guides arrive on site for 6pm.
1730 | Staff set-up space at Thoresby Primary School
1830- 1845 | Chior arrive & prepare veils, lanterns, ponchos (if required due to wet weather)
1845 - 1915 | Choir massed rehearsal & show notes (warm-up, opening & finale, general notes)
1915 - 1945 | 30min - split rehearsal?
2000 - 2035 | SITE WALK-THROUGH, BLOCKING REHEARSAL. Site Briefing.
2035 | 10min call for 2115 technical rehearsal start
2045 | Singers and Guides walk to show start places
2115 - 2230 | Technical Rehearsal
Wednesday, May 17th | DRESS REHEARSAL - Singing Guides & Guides arrive on site for 6pm
1730 | Staff set-up space at Thoresby Primary School
1830- 1845 | Chior arrive & prepare veils, lanterns, ponchos (if required due to wet weather)
1845 - 1915 | Choir massed rehearsal & show notes (warm-up, opening & finale, general notes)
1915 - 1945 | Split choir reh. Large ensemble rehearsing in the large hall. Smaller group rehearsing in the hallway.
2000 - 2035 | SITE WALK-THROUGH
2035 | ALL into Costume
2045 | Singers and Guides walk to show start places
2115 - 2230 | Dress Rehearsal (no audience, no CIRCA acrobats)
Thursday, May 18th | SHOW 1 - Singing Guides & Guides arrive on site for 7pm
1830 | Staff set-up space at Thoresby Primary School
1930 - 2000 | Chior arrive & prepare veils, lanterns, ponchos (if required due to wet weather)
2000 - 2035 | Choir massed rehearsal & show notes (warm-up, opening & finale, general notes)
2035 | ALL into Costume
2045 | Singers and Guides walk to show start places
2115 - 2230 | SHOW 1
Friday, May 19th | SHOW 2 - Choir & Guides arrive on site for 7pm
1830 | Staff set-up space at Thoresby Primary School
1930 - 2000 | Chior arrive & prepare veils, lanterns, ponchos (if required due to wet weather)
2000 - 2035 | Choir massed rehearsal & show notes (warm-up, opening & finale, general notes)
2035 | ALL into Costume
2045 | Singers and Guides walk to show start places
2115 - 2230 | SHOW 2
Saturday, May 20th | SHOW 3 AND 4 - Singing Guides & Guides arrive on site for 5pm
1630 | Staff set-up space at Thoresby Primary School
1700 - 1730 | Chior arrive & prepare veils, lanterns, ponchos (if required due to wet weather)
1730 - 1815 | Choir massed rehearsal & show notes (warm-up, opening & finale, general notes)
1815 - 18.35 | Split choir rehearsal
1835 | ALL into Costume
1845 | Singers and Guides walk to show start places
1915 - 2015 | SHOW 3
2015 - 2115 | Reset. All to remain in Costume.
2115 - 2230 | SHOW 4
Sunday, May 21st | SHOW 5 - Singing Guides & Guides arrive on site for 7pm
1830 | Staff set-up space at Thoresby Primary School
1930 - 2000 | Chior arrive & prepare veils, lanterns, ponchos (if required due to wet weather)
2000 - 2035 | Choir massed rehearsal & show notes (warm-up, opening & finale, general notes)
2015 - 20135 | ALL into Costume
2035 | 10min call for 2115 technical rehearsal start
2045 | Singers and Guides walk to show start places
2115 - 2230 | SHOW 5