| Assessment of: | Frogman | Assessment carried out by: | Joanna Morley (JM) and Martin Atkinson (MA) |
| --- | --- | --- | --- |
| Assessment number: | 2 | Position: | Production Assistant and Producer |
| Date: | 01/11/17 | Review date: | 02/11/17 |
| Second Floor Block C, C4DI |  | - Venue & Fire - Audience & Public |  |

| No. | ACTIVITY & WHO IS AT RISK | HAZARDS PRESENT | EXISTING CONTROL MEASURES | No. at risk | Risk factors |  |  | FURTHER ACTION REQUIRED & BY WHOM | DATE OF ACTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Likelihood | Severity | Risk Level |  |  |
| 1.0 | Fire & Emergencies | Emergency Evacuation Potential Outcomes: Panic, delays of time, severe physical injury | Venue’s existing fire evacuation procedures are to be followed. Venue Manager to conduct briefing for all staff on site prior to work. Venue Manager and Volunteers given notes, briefing and time on site prior to event to familiarise themselves with exits and assembly points. Wheelchair users to be placed at the evacuation point on the stairwell and safely carried in a stable chair with arms down the stairs. Consulted with fire operations people for the building and confirmed procedure in accordance to their recommendations. 4 people will be present to help the wheelchair user out of the building. | 60 | 1 | 5 | LOW | All fire escape routes to be kept clear at all times | 01/11/17-11/11/17 |
| 1.1 | Rigged lights heating wall and ceiling surfaces | Potential fire hazard. Potential Outcomes: Burns, serious injury, death | Lights have been moved away from ceilings and surfaces and only remain on when required for performance. | 60 | 2 | 5 | MEDIUM | Stage Manager, Duty Tech and Venue Manager to monitor all lamps and lights throughout the run. Stage Manager only turning on lights when they are required for the performance or focusing. | 01/11/17-11/11/17 |
| 2.0 | Public unfamiliar to venue layout (audience configuration including rubber matting and use of Virtual Reality, monitors and headphones). Members of the public | Unfamiliar egress in emergency evacuation. Potential Outcomes: Falls and accidental collisions Panic and delays in evacuation | Venue Manager will familiarise themselves with the auditorium as well as designated volunteers to direct audiences around specific routes. Volunteers to be positioned in the auditorium to alert audiences to hazards. Route to fire exit kept clear at all times and indicated in a show-stop. | 60 | 2 | 2 | LOW | First Aid will be present via Stage Manager of curious directive. Adequate lighting for public’s visibility during access and egress will be set. All house lights raised in an emergency situation. Emergency lighting is in place. Seating available for those who desire it. | 01/11/17-11/11/17 |
| 2.1 | Lighting Fixtures in close proximity to the audience. Members of the public. | Injuries caused. Potential Outcomes: Crushing injury, trips and falls. | Fixtures have been rigged by and are to be checked by competent personnel before each performance. Trip hazards to be clearly marked out for audience members. Volunteers to be positioned in the auditorium to alert audiences to hazards. | 60 | 2 | 2 | LOW | All structures to be signed off by competent person prior to performance. | 01/11/17-11/11/17 |
| 2.2 | Lighting for evacuation purposes whilst performance is running | Injuries caused, route to exit not clear. Potential Outcomes: Crushing injury, trips and falls. | Lights have been set to a level where route to the exit can be found easily. No obstructions on the route. Lights from corridor remain on during performance. If power is to go, emergency lights will come on. | 60 | 1 | 2 | LOW | Venue Manager to set lighting to required level each performance. | 01/11/17-11/11/17 |

RISK MATRIX

| LIKELIHOOD SEVERITY | 1. Very unlikely (no known history) | 2. Unlikely (unlikely sequence of events) | 3. Possible (Foreseeable under unusual circumstances) | 4. Likely (Easily foresseable – some incidents may have occurred) | 5. Very likely (Common occurrence – aware of incidents) |
| --- | --- | --- | --- | --- | --- |
| 1. Negligible (no visible injury – no pain) | LOW | LOW | LOW | LOW | LOW |
| 2. Slight (minor cuts or bruises – no long term effects) | LOW | LOW | LOW | MEDIUM | MEDIUM |
| 3. Moderate (Heavy bruising, deep wounds, lost time) | LOW | LOW | MEDIUM | MEDIUM | HIGH |
| 4. Severe (Major injuries, lost time accidents, RIDDOR reportable) | LOW | MEDIUM | MEDIUM | HIGH | HIGH |
| 5. Very Severe (Long term disability or death) | LOW | MEDIUM | HIGH | HIGH | HIGH |

| NAME OF ASSESSOR: |  | DATE OF ASSESSMENT: |  |
| --- | --- | --- | --- |
| SIGNATURE: |  |  |  |
| CONTACT DETAILS |  |  |  |
| EMAIL: |  | PHONE: |  |