## Sheet1
MACNAS - Marketing overview
|  |  |  | Oct |  |  |  |  | Nov
Activity | Production Notes | Size/Dimensions/ Quantity | Deadlines | 2nd | 9th | 16th | 23rd | 30th | 6th | COST | Notes
Door Drops
East Park - Seven Alley's audience | HOLDERNESS RD. James Reckitt Ave Summergangs Road & area around East Park DISTRIBUTION to start: Mon 23rd Oct | x 10,000 households | For booking: Mon 9th Oct For artwork: Thur 12th Oct | [6 empty] | 950 | Based on solus distirbution | bar: Oct 23rd
Longhill - Longhill Burn audience | LONGHILL. Eastmount - houses around Eastmount Community Centre Weaver Grove - houses around Weaver Grove Cam Grove and Limerick Close and other areas in Longhill estate DISTRIBUTION to start: Mon 23rd Oct | x 4743 households | For booking: Mon 9th Oct For artwork: Thur 12th Oct | [6 empty] | 215 | Based on shareplan distribution | bar: Oct 23rd
Bransholme - GNGG audience | Area surrounding North Point Shopping Centre DISTRIBUTION to start: Mon 23rd Oct | x 2,326 households | For booking: Mon 9th Oct For artwork: Thur 12th Oct | [6 empty] | 338 | Based on solus distribution | bar: Oct 23rd
Pickering Park - Voice Park audience | Area surrounding Pickering Park DISTRIBUTION to start: Mon 23rd Oct | x 5,868 households | For booking: Mon 9th Oct For artwork: Thur 12th Oct | [6 empty] | 558 | Based on solus distirbution | bar: Oct 23rd
Springhead Pumping Station - Micropolis audience | Area around Anlaby Road DISTRIBUTION to start: Mon 23rd Oct | x 5,921 households | For booking: Mon 9th Oct For artwork: Thur 12th Oct | [6 empty] | 1176 | Based on solus distirbution | bar: Oct 23rd
Print for Door Drop activity | 360x250, folded to 180x125mm Full colour both sides 150gsm uncoated (recommended stock) x35,000 | x 35,000 Copies to fulfil all doordrop locations (with around 5,000 extra) | Artwork approval for print: Thur 12th Oct | [6 empty] | 2765 | bar: Oct 23rd
| Delivery to BKR and 2 x Hull Addresses. | [8 empty] | 50 | Delivery | bar: Oct 23rd
Orchard Park - New Audience | Area around Hall Road/ Orchard Park Road DISTRIBUTION PLANNED FOR: Wed 8 Nov | x 3,500 households | For booking: Wed 1st Nov For artwork: Wed 1st Nov | [6 empty] | 426 | Based on solus distribution | bar: Nov 6th
Print for Door Drop activity (wave 2) & Surplus |  | x5,000 copies of print (3,500 for door drops and 1500 for general use) | [7 empty] | 740 | 3,500 to be delivered to BKR. 1,300 to go to the pod. The remaining 200 to come to Lowgate House. | bar: Nov 6th
Newspaper
Hull Daily Mail Weekend Supplement | Saturday insertion in the HDM. 2 insertions: Saturday 28th October and Saturday 4th November | Full Page - 340mm h x 270mm w | For booking: Wed 18th Oct For artwork: Wed 25th Oct | [6 empty] | 1100 | bar: Oct 23rd to Oct 30th
Newspaper
Hull What's on | Local website. Middle package. 25,000 views of 10 second or more. 4 display banners across 6 spots per page on rotation with other clients. ROS. Promoted Facebook event based post of 5,000-10,000 reach. | 4 x sizes TBC | For booking: For artwork: | [6 empty] | 360 | To start w/c Mon 23rd October until Sat 11th Nov. | bar: Oct 23rd to Oct 30th
Ecowashing
20 x city centre washes - along parade route | Parade Route Map provided to supplier for quoting purposes |  | Booked | [6 empty] | 800 | Andy P to complete 2nd/3rd Nov to tie in with crate activity happening on 4th Nov | bar: Oct 23rd to Nov 6th
Vinyls/ heralding moment
Window vinyl print for heralding moment for Macnas | For end unit of Whitefriargate/ LOGG (covering where the red graphics are currently situated - the Hull map needs to remain) | See separate document for dimensions. | Booking deadline: Mon 9th Oct Artwork deadline: Mon 16th Oct | [6 empty] | 908 | John E Wrights booked in for install. This is based on install on 20th October. | bar: Oct 16th to Nov 6th
Posters / flyers
A4 posters | To cover the city centre - shops, cafes, restaurants etc. To be distributed by volunteers. Surplus posters have been sent to Primary Schools for distribution via the HCC network. | 150 x A4 Posters | Artwork deadline: Mon 16th Oct | [6 empty] | 76 | Happy to go ahead with this John. | bar: Oct 23rd to Nov 6th
Creative charges
To complete all of the above | [9 empty] | £1000 - £2500 | Estimated cost only. We can confirm this once all artwork items have been briefed in to the designer.
Digital/Social media
Facebook, Twitter - sponsored posts and targeted advertising | [9 empty] | 1000 | Estimated cost only. We need to speak to Chris Marr with a brief so he can advise on the detail for activity and spread of when this would take place. | bar: Oct 16th to Nov 6th
Ad messenger | See separate doc for info about this service - it's new, but potentially worth a try. It will help us monitor interaction with specific postcode areas/demographics x 100,000 impressions (minimum order) | Spec TBC | Booking deadline: Fri 13th Oct | [6 empty] | 700 | Based on 100,000 impressions. Booked with F&T. | bar: Nov 6th