DESIGNER BRIEF

POP-UP POETRY STATION

General Brief

Design & build a Pop-up Poetry Station for poet Bohdan Piasecki’s work with the Polish community in Hull.

The Pop-up Poetry Station will be set up in a variety of public spaces (outdoors and/or indoors) and will be used to attract attention and invite passers-by to sit down with Bohdan, talk to him, have him write poems for them, and invite them to write alongside him & record their stories.

The goal is to create an easily transportable piece of mobile/foldaway/wheeled furniture which will fulfill the following requirements:

- portable (fits in a car or small van and can be deployed by one person)

- attractive design (eye-catching, will have people asking questions)

- can accommodate at least two people sitting down

- has adequate writing space for at least two people

The specifics of the design are entirely up to the designer  - for reference and inspiration, here is a (tiny) Pinterest board Bohdan created whilst researching the idea: https://uk.pinterest.com/beveryquiet/pop-up-poetry-station-inspiration/

The Pop-up Poetry Station will be used over the summer months. If suitable, it may then be incorporated in the more permanent space which will open in September.

Dates

- Initial design ready by June 4th

- Final design approved by June 18th

- Pop-up Station built and ready for use by July 5th

Budget

The budget is set at £2000 to include all costs, including design, build, and materials.