## Sheet1
Caravan of Love
Draft Schedule for Sean McAllister_version 2
week beginning | days |  | activity | milestones & phases
2016-01-11 |  | Research, concept & design development
2016-01-18
2016-01-25 | 5 |  | initial research and partner meetings
2016-02-01 | 3 |  | R&D and creative development, meet potential creative team
2016-02-08 | 3 |  | R&D and creative development, meet potential creative team | appoint creatives
2016-02-15 | 2 |  | meetings & concept developemnt | appoint creatives
2016-02-22 | 1 |  | meetings & concept developemnt | contract creatives
2016-02-29 | 2 |  | meetings & concept developemnt
2016-03-07 | 1 |  | present concept | Initial concept delivered
2016-03-14 | 2 |  | design meetings | design work
2016-03-21 |  |  |  | design work
2016-03-28 | 2 |  | design meetings | design work
2016-04-04 | 1 |  | design meetings | design work | archiving roadshow
2016-04-11 |  |  |  |  | archiving roadshow
2016-04-18 | 1 |  | present design concept | initial design delivery | archiving roadshow
2016-04-25 |  |  |  | procurement | archiving roadshow
2016-05-02 | 2 |  | design meetings | procurement | archiving roadshow
2016-05-09 |  |  |  | procurement | archiving roadshow
2016-05-16 | 2 |  | design meetings | procurement
2016-05-23 |  |  |  | procurement
2016-05-30 | 1 |  | design meetings | procurement
2016-06-06 |  | Creative & content development
2016-06-13
2016-06-20 | 1 |  | design presentation | final design delivered
2016-06-27 | 3 |  | script & content meetings |  | script & content development
2016-07-04 | 2 |  | script & content meetings |  | script & content development
2016-07-11 | 1 |  | script & content meetings |  | script & content development
2016-07-18 |  |  |  |  | script & content development
2016-07-25 |  |  |  |  | script & content development
2016-08-01 | 2 |  | script & content meetings |  | script & content development
2016-08-08 |  |  |  |  | script & content development
2016-08-15 | 2 |  | script & content meetings |  | script & content development
2016-08-22 |  |  |  |  | script & content development
2016-08-29 |  |  |  |  | script & content development
2016-09-05 |  | delivery |  | Programme launch | script & content development
2016-09-12 | 2 |  | auditions & pre production meetings |  | volunteer cast auditions
2016-09-19 | 2 |  | auditions & pre production meetings |  | volunteer cast auditions
2016-09-26 | 2 |  | auditions & pre production meetings | Technical specs finalised | volunteer cast auditions
2016-10-03 | 2 |  | pre production meetings
2016-10-10
2016-10-17 | 2 |  | pre production meetings
2016-10-24
2016-10-31 | 2 |  | pre production meetings
2016-11-07
2016-11-14 | 2 |  | pre production meetings
2016-11-21 | 2 |  | professional cast rehearsals | Rehearsals begin
2016-11-28 | 2 |  | professional cast rehearsals
2016-12-05 | 2 |  | full company rehearsals (including volunteer cast)
2016-12-12 | 2 |  | full company rehearsals (including volunteer cast)
2016-12-19 | 3 |  | full company rehearsals (including volunteer cast)
2016-12-26 | 3 |  | full company rehearsals (including volunteer cast)
2017-01-02 | 5 |  | full company rehearsals (including volunteer cast) | onsite build | onsite rehearsals
2017-01-09 | 6 |  | tech rehearsals & perfs
total days: | 78