Hull 2017/Blade

Rev.  Cost Estimates AK 071216 v2

| Description | Notes…………………….. | Estimate |
| --- | --- | --- |
| 1.Costs to date 2.Transportation/SF Removal – North Midland Advance Removal/Replacement of Street Furniture Install: 3nr teams night of transport, labour, vehicles & equipment Removal: 3nr teams night of transport, labour, vehicles & equipment 3.Support Structure – Pearl Green Root, tip & passive ‘barriers’ Trial & Installation (labour, plant, materials) ‘Anti-climb’ pc sum 4.Installation Security/Pedestrian Control Lighting Route security & Police attendance, delivery & removal 5.Display, Maintenance & Security Site signage Pressure Wash Cleaning Security 24/7 PC for ‘reactive’ maintenance Disposal/Making Good (Eurovia) 6.Fees Artist Commission Fee (inc. expenses) Structural Design, Consents, H&S, Project Management TOTAL |  | £21,500 £175,000 £64,500 £20,000 £5,000 £89,500 £1,000 £3,000 £7,000 £11,000 £1,800 £3,200 £25,000 £5,000 £10,000 £45,000 £13,000 £50,000 £63,000 £405,000 |