Minutes: Producing Project team meeting: 09.03.2017

Slung Low: Flood

Present: Martin Green (MG), Lindsey Alvis (LA), Gareth Hughes (GH), David Watson (DW), Martin Atkinson (MA)

Actions in bold.

Tabled Risk Register & Roles & Responsibilities to be reviewed.

- Volunteer conversation: need to address with Slung Low.

  - GH has drawn up points of where volunteers should be distributed and conversation needs to start with HJ in order to see what numbers we might need.

- Ask Harriet about site volunteer numbers. MA to sit with Harriet.

  - MA has requested meeting, HJ just clearing her desk from WOW.

- Rachel needs to assist with wayfinding. Appoint to make signs, etc.

  - Meeting with RC and GH has been arranged for Tuesday afternoon to locate suitable signage points.

- Review risk register numbers following the meeting.

- Car parking: engage Prestige.

  - GH has connected with Prestige, and has taken communication from The Deep to arrange parking.

- Things have been forgotten, we need to interrogate site management further.

  - Gareth to interrogate that and put plans in place.

- Use judgement on what isn’t being achieved.

  - GH with site plans to determine this.

- Car Parking message: the reason why we tell people to not drive is because we want to be a green event. If you must drive, here is the car park. Please do not park anywhere else, as this is a disturbance to residents.

  - David to send out messaging around public transport and getting to site.

- We are there to help fill the gaps in terms of what hasn’t been provided.

- As SL are lead producing the event, Hull 2017 team do not need to be on radios. However, clear lines of communication to be in place for the event should anything arise.

- Hull 2017 do a crisis comms plan. Comes down more to cancellation weather.

  - Ben and Lindsey to take this forward and establish what kind of weather stops this show?

- Show Reports: Slung Low responsibility, to be circulated to full project team for review.

  - Gareth to keep checking in with them when he can and remind them of this.

- MA to check with Harriet that she is happy with volunteers treatment of performers and how we manage the site vols.

- Hull 2017 to be kept informed on SL communication with residents. Martin to speak to Al.

- Wheelchair use:

  - Gareth to look at site and the placing of this. Find out how many wheelchair users planning to attend.

- MA and GH to liaise with vols.

- MA: wayfinding, vols, FAQs to box office.