Epicycle 02.08.17

Attending: Lily, Hannah, Katy, Michael, Michelle, Rachel, Adam (by phone)

| To Do | Lead | Notes |
| --- | --- | --- |
| Book in Van advert | Rachel |  |
| Look at ‘circus’ email sign ups and proposal for a more targeted email | Michelle |  |
| Widen social media capture zone to the Aves (Friday) | Michelle |  |
| Site Dressing Plan | Rachel |  |

Marketing

- Rachel to organise a van advert for either Wednesday or Sunday when Walton St Market is on. Will drive round the area for 8 hours.

- Could target KCom and partners

- Site dressing plan to come from Rachel – Rachel on a site visit tomorrow AM to look at tree trunks/gates for site rules. Normal branded banners on fencing. To go up Friday and de-rig on Monday.

- Get flags and look at them on site – 1x toilets – Security can bring them in overnight.

Digital

- Michelle to look in to how many people have signed up to the ‘Circus’ email category and look at doing a more targeted email

- Event page is live – around 3,500 unique page views

- Widen social media capture zone to the avenues on Friday, to be reviewed on Monday

- Tues/Weds we go wider with social media, photos from the build, on main feed

Production

- Andrew Wilson on leave until Friday so no updates about the paths

- First Aid to go next to accessible parking so they can get straight out

- Parking signage is in Adam’s budget