## Sheet1
ROYAL BALLET RELAY AT QUEENS GARDENS
Schedule (this schedule is subject to change)
FRIDAY 15 SEPTEMBER
6:00 | Rubbish Pick | Hull City Council
10:00 | Site mark Up | Hull 2017
12:00 | First Aid on Site | North East Medical
| Build of screen support structures and Ballast | HPSS
| Security on site for asset protection | Prestige
| Build of stage tent | Tentickle
13:00 | Delivery and Install Generators / temporary power | Elecplant
15:00 | Build of stage | HPSS
20:00 | Site Clear of all contractors | All
0:00 | Security changeover (asset protection) | Prestige
SATURDAY 16 SEPTEMBER
8:00 | Delivery and Install of screens | Lightmedia
| Build of concessions and bars | HC&L
9:00 | Delivery of Barrier | All Occasions
Install of PA, Stage Lighting and FOH postion
| Delivery and install of portaloos | Addplant
10:00 | Links Broadcast arrive on site
| Barrier install (Phase 1 - permieter) | Local Crew
12:00 | Security Changeover | Prestige
13:00 | Erection of Information / Welfare marquee | Local Crew
14:00 | Testing (PA, Screens, Broadcast Link)
15:00 | SIA and Stewards Event Briefing | Prestige
| Road Closures in effect | SEP
| Bins delivered and distributed across site | Hull City Council
16:00 | Barrier Install (phase 2 - ticket gates) | Local Crew
| Event First Aid onsite | North East Medical
| Volunteer arrival for Briefing at 16:30 | Hull 2017
17:15 | Volunteers Deployed | Hull 2017
18:00 | GATES OPEN
19:30 | Relay Commences | Links Broadcast
22:00 | Relay Ends | Links Broadcast
22:30 | Audience clear of site
22:30 | Cleansing of site commences | Hull City Council
22:45 | De-rig of screens commences | Lightmedia
22:45 | Derig Commences (Sound, lighting, and stage) | HPSS
23:00 | Roads Re-opened (except Guildhall Road) | SEP
0:00 | Security Changeover | Prestige
SUNDAY 17 SEPTEMBER
10:00 | Removal of toilets | Addplant
| Removal of generators | Elecplant
| De Rig of Screen Structures | HPSS
| Bins Collected and taken off site | Hull City Council
| Conessions and Bars infrastructure removed | HC&L
14:00 | Barrier Collection | All Occasions
16:00 | Site Clear and Handover