## Sheet1
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | More notes 08/04 | INVOICE RECEIVED | INVOICE PAID | Insurance values
LIGHTING
Show Lighting - O1 | Nitelites | 2905.18 |  |  | fixtures and rigging only |  | ordered 27/04 |  | 2017-05-05 |  | 220000
cabling | Nitelites | inc above |  |  | Need to work out |  | ordered 27/04 |  | 2017-05-05 |  | inc above
delivery | Nitelites | 816 |  |  |  |  | ordered 27/04 |  | 2017-05-05 |  | inc above
Holding area light | Nitelites | inc above |  |  |  |  | ordered 27/04 |  | 2017-05-05 |  | inc above
entrance path lighting | Nitelites | inc above |  |  |  |  | ordered 27/04 |  | 2017-05-05 |  | inc above
consumables | Nitelites | 93 |  |  | gel & blackwrap |  | ordered 27/04 |  | 2017-05-05
Festoon | TGE | 200 | [8 empty] | inc above
additional cabling | 3d | 40.8 | [6 empty] | 2017-05-15
LIGHTING SUB-TOTAL |  |  |  | 4054.98
AUDIO
Main Audio - O1 | 3d | 2106.1 |  |  | as spec | delivery in with lighting | ordered 14/04 |  | 2017-05-15 |  | 127000
batteries | 3d | inc above |  |  | for radio mics |  | ordered 14/04 |  | 2017-05-15 |  | inc above
PA tech | 3d | 1320 |  |  | £220 per day |  | ordered 14/04 |  | 2017-05-15 |  | inc above
accom/subs | 3d | 421 |  |  | accomodation & PD's |  | ordered 14/04 |  | 2017-05-15 |  | inc above
Holding area PA | 3d | 734.25 |  |  | 4 x boxes on stands - Y7p's | each corner | ordered 14/04 |  | 2017-05-15 |  | inc above
Promenade PA | 3d | 167.79 |  |  | drive, cabling and rigging |  | ordered 14/04 |  | 2017-05-15 |  | inc above
missing cables | 3d | 73 |  |  | 3 xlr's went missing |  |  |  | 2017-05-15
Promenade PA | TGPS | 100 |  |  | 8 x A-parts | and cabling | ordered 14/04 |  |  |  | inc above
additional cabling | electric centre | 24 |  |  |  |  | bought 03/05 |  | receipt | on credit card
Transport | 3d | 310 |  |  | delivered Sunday @ 2pm |  | ordered 14/04 |  | 2017-05-15 |  | inc above
anounce mics | Maplins | 33.32 |  |  |  |  | bought 03/05 |  | receipt | on credit card
AUDIO SUB-TOTAL |  |  |  | 5289.46
STRUCTURES
promenade control position | TGE | 50 |  |  | black gazebo | [5 empty] | 300
control position | 3D | 250 |  |  | 4m x 3m @ 0.5m | inc delivery & build | ordered 14/04 |  | 2017-05-15 |  | 2500
ladders | 3D | 47.28 |  |  | 1 x 10 rung & 1 x 14 rung |  | ordered 14/04 |  | 2017-05-15 |  | 300
build | 3D | 220 | [6 empty] | 2017-05-15 |  | -----------------
production/dressing room tent | Nationwide | 465 |  |  | 9m x 6m with lighting |  | ordered 12/04 |  | 2017-05-09 |  | 5800
volunteer tent | periplum bringing | 0 |  |  | periplums army tent |  |  | periplum emailed 08/04 |  |  | -----------------
furniture | Nationwide | 95.5 |  |  | 10 x tables, 40 x folding chairs |  | ordered 12/04 |  | 2017-05-09 |  | 880
additional chairs | Nationwide | 58 |  |  | 40 additional chairs, for audience | £1.45 per chair | ordered 12/04 |  | 2017-05-09 |  | 480
del/coll | Nationwide | 250 |  |  |  |  | ordered 12/04 |  | 2017-05-09 |  | -----------------
STRUCTURES SUB-TOTAL |  |  |  | 1435.78
POWER & DISTRO
Distro | IDE | 1549 |  |  | as spec, inc 40 panels cable ramp |  | ordered 24/04 | waiting on plan, emailed Dave to say what's going on |  |  | 18500
Delivery | IDE | inc above |  |  |  |  | received quote 14/03 |  |  |  | -----------------
show generators | John F Hunts | 600 |  |  | 2 x 100KVA | syncd to load share | ordered 20/04 | Emailed Jean to let her know where we're at |  |  | 46000
tank | John F Hunts | 20 |  |  | 1000l bunded tank |  | ordered 20/04 |  |  |  | 1500
Production set | John F Hunts | 135 |  |  | 40kva pink |  | ordered 20/04 |  |  |  | 9000
tank | John F Hunts | 20 |  |  | 1000l bunded tank |  | ordered 20/04 |  |  |  | 1500
Exit set | John F Hunts | 135 |  |  | 40kva pink |  | ordered 20/04 | Need to work out if we need |  |  | 9000
Entry set | John F Hunts | 135 |  |  | 40kva pink |  | ordered 20/04 |  |  |  | 9000
bowser | John F Hunts | 40 |  |  | 1000l towable bowser |  | ordered 20/04 |  |  |  | 3500
fuel | John F Hunts | 700 |  |  | as used | ESTIMATE |  |  |  |  | 2701
tower lights | John F Hunts | 240 |  |  | 2 x LED tower lights |  | ordered 20/04 |  |  |  | 2100
del/coll | John F Hunts | 1320 |  |  | delivered Sat and collected Sun |  | ordered 20/04 |  |  |  | -----------------
POWER & DISTRO SUB-TOTAL |  |  |  | 4894
PLANT & BARRIERS
Plant | Add plant | 275 |  |  | 9m telehandler | to move generators and fencing | ordered 13/04 | emailed Jon to tell we would be ordering by the middle of the week |  |  | 35000
del/coll | Add plant | inc above |  |  | sat 29th/Sun 7th |  | ordered 13/04 |  |  |  | -----------------
ped barriers | Actavo | 412.5 |  |  | 150 panels | May need more | ordered 26/04 |  |  |  | 5700
Heras Fencing | Actavo | 120 |  |  | 40 sets |  | ordered 26/04 |  |  |  | 1720
Debris mesh | Actavo | 74.82 |  |  | 3 x rolls of black debris mesh |  | ordered 26/04 |  |  |  | 150
del/coll | Actavo | 200 |  |  |  |  | ordered 26/04 |  |  |  | -----------------
PLANT SUB-TOTAL |  |  |  | 1082.32
CREW
Local crew | The Music Consortium | 1545 |  |  | 2 crew Sat 1000-1800, 4 crew Sun 0900-1700, 2 crew Weds 1000-1800, 6 crew Sat 1030-0230, 2 crew Sun 1000-1400 |  | ordered 05/04 |  |  | 2017-04-24 | -----------------
Tech Crew | freelancers | 800 |  |  | 1 person Sun - weds | 4 days @ £200 pmpd 1 half day at @ £120 | ordered 26/04 | Danny Owen |  |  | -----------------
Tech Crew | The Music Consortium | 412 |  |  | 1 Person Sun & Mon |  |  |  | 2017-04-26 | ??
additional crew | The Music Consortium | 247.2 |  |  | 2 extra crew sun 1000-1800 |  |  |  | 2017-05-05
additional crew | freelancers | 400
mileage/expenses | freelancers | 380 |  |  | Danny PD's & mileage
CREW SUB-TOTAL |  |  |  | 3784.2
MISCELLANEOUS
ballast | MKM | 150 |  |  | 100 x 25kg bags of sand | £1.50 per bag | ordered 26/04 | quote ref 1645340 | receipt | on credit card | 150
hessian | J&C Joels | 196.8 |  |  | 100m x 1.78m wide | to buy | ordered 24/04 | work out how much |  | on credit card | 192
rope | ropes direct | 53.8 |  |  | 440m of 6mm manila |  | ordered 24/04 |  |  | on credit card | 53.8
additional pins | MKM | 144 |  |  | 60 of |  | ordered 02/05 |  | receipt | on credit card
additional hessian | MKM | 90.52 |  |  | 100m of |  | ordered 02/05 |  | receipt | on credit card
additional hessian | MKM | 90.52 |  |  | 100m of |  | bought 03/05 |  | receipt | on credit card
additional hessian | MKM | 45.26 |  |  | 50m of |  | bought 03/05 |  | receipt | on credit card
additional rope | MKM | 32.4 |  |  | 440m of 6mm blue draw |  | ordered 02/05 |  | receipt | on credit card
additional rope | ropes direct | 30.65 |  |  | 220m of 6mm manila |  | ordered 02/05 |  |  | on credit card
catering supplies | Petty cash | 5 |  |  | cups, tea, coffee | Maddie has cups, 17 has water, LOGG house has tea & coffee. Just need milk |  | Gareth to supply burco's, do 2017 have supplies |  |  | 10
consumables | mkm | 75.31 |  |  | tape, cable ties etc |  | bought |  | receipt | on credit card
comms | Events team | 0 |  |  | 40 x DP3400's | inc chargers | Gareth booked | Check with Johnny B that they have surveillance earpieces - emailed 10/04 |  |  | 21000
accessories | 900 comms | 20 |  |  | 2 x noise cancelling headsets |  | ordered 08/04 |  |  |  | 150
del/coll | 900 comms | 25 |  |  | delivered 27th April to pacific exchange | to TGE | ordered 08/04 |  |  |  | -----------------
Cleansing | Hull CC | 672.72 |  |  | Sweep each morning after show | emailed Steve Mckee | ordered 08/04 |  |  |  | -----------------
Bins | Hull CC | 222 |  |  | 4 x 1100l bins | delivered Fri, collected Mon | ordered 12/04 |  | 2017-05-15
backstage toilets | add plant | 300 |  |  | 6 x single plastics | delivered Saturday | ordered 13/04 | emailed Jon to tell we would be ordering by the middle of the week |  |  | 3600
service | add plant | 240 |  |  | Mon, Weds |  | ordered 13/04 |  |  |  | -----------------
Audience toilets | add plant | 860 |  |  | 14 x single plastics and 2 x wheelchair accessible units |  | ordered 13/04 |  |  |  | 10800
servicing | add plant | 795 |  |  | service Thurs, fri & sat |  | ordered 13/04 |  |  |  | -----------------
del/coll | add plant | 190 |  |  |  |  | ordered 13/04 |  |  |  | -----------------
Trakway | GAP | 600 |  |  | 50 x Groundguards |  | ordered 10/04 |  | 2017-05-12 |  | 7500
Delivery & collection | GAP | 190 |  |  | delivered Friday, Collected Monday |  | ordered 10/04 |  | 2017-05-12 |  | -----------------
ground works | pbs construction | 1350 |  |  | to make path safer | Do Fri 28th | ordered 13/04 | emailed to inform that we will be the ones paying, 08/04 | 2017-05-04 |  | -----------------
scaff | actavo | 56.24 |  |  | just in case |  | ordered 26/04 |  |  |  | 75
MISCELLANEOUS SUB-TOTAL |  |  |  | 6435.22
STEWARDING
Stewarding & security - O2 | Prestige | 9661 |  |  | all as per spreadsheet |  | sent Justine updated spreadsheet 05/04 |  | 2017-05-15 |  | -----------------
morrisons stewards | Prestige | 567 |  |  | 3 stewards to cover carpark |  | updated quote 20/04 |  | 2017-05-15 |  | -----------------
additional stewards | Prestige | 126 |  |  | 3 additional staff for Saturtday |  |  |  | 2017-05-15
Lost kids | Prestige | 504 |  |  | cover for show nights |  | received quote 06/04 |  |  |  | -----------------
STEWARDING SUB-TOTAL |  |  |  | 10858
H&S
Show first aid | Heart Medical | 4404 |  |  | 6 x first aiders, ambulance & 2 x paramedics |  | ordered 13/04 |  |  |  | -----------------
additional show first aid | Heart Medical | 200 |  |  | 2 first aiders starting early 1800-2000 | £50 per day | ordered 13/04 |  |  |  | -----------------
rehearsal first aid | Heart Medical | 336 |  |  | 2 first aiders for 2 rehearsals |  | ordered 13/04 |  |  |  | -----------------
Fire extinguishers | TGPS | 50 | [8 empty] | 350
H&S SUB-TOTAL |  |  |  | 4990
TM
cones | Actavo | 268 |  |  | 40 x no waiting cones | for blue badge parking | ordered 26/04 |  |  |  | 268
TM SUB-TOTAL |  |  |  | 268
FEES
Handling fee | TGPS | 2154.598 |  |  | 5% of all hires | [5 empty] | -----------------
FEES SUB-TOTAL |  |  |  | 2154.598
TOTALS Ex Contingency, Ex VAT |  | 45246.558
Contingency |  | 753.442
TOTALS inc Contingency - EX VAT |  | 46000 | [8 empty] | 546779.8
TOTAL inc VAT |  | 54000
First invoice |  | 22500
Final invoice |  | 22772.96
Total |  | 45272.96
Discrepency |  | 26.402 | Signed off