LOGG

On site days

FULL DAY 	29th August – Joshua get-in

FULL DAY	30th August – Joshua get-in

FULL DAY	31st August – Joshua live. Scottee get in begins

FULL DAY	1st September - Scottee get-in

(2nd September – Scottee live. Half day) possibly not needed

(4th September – Scottee get-out) – prob not needed.

FULL DAY	5th September – Joshua get-out.  Plus get-in of interior rig for Mcguires.

HALF DAY	7th September – McGuires get-in.  If they get here on time.  Half-day

HALF DAY	8th September – Mcguires get-in.  Half-day

HALF DAY	9th September – McGuires live.  Try for half day

HALF DAY	10th September – Mcguires live.  Try for half day

HALF DAY	11th September – Mcguires Live, then get-out.  Try for half day

FULL DAY	22nd September – Periplum prep day?

HALF DAY	23rd September – Periplum live. Half day

FULL DAY	27th September – accomm only?

FULL DAY	28th Sept – Dominic at market.  Thor.  Periplum prep

FULL DAY	29th Sept – Dominic and Thor (full get-in).  Periplum live too.

(30th Sept- probably not needed)

FULL DAY	1st October – Thor get-out

FULL DAY	2nd – possible Periplum culmination

This adds up to 11 days 6 half days.

11 X £350 = 	£3850

6 X £200 = 	£1200

Office/meeting days

Meeting on 10th

Meeting 15th

Meeting / working in Hull day 17th

Meeting / working in Hull day 24th

5 additional office days

= 9 days @ £250 = £2250

TOTAL = £7300

+

PDs @ £20? For 12 days = 	£240

Mileage 11 return journeys = attempt to get this thrown in with the fee.  Otherwise £660.

On top of this I would need accommodation for 11 nights